## Budet-2016-17
Annual work plan & Budget 0f OPELIP for the year 2016-17
Code | Sl No. | Component/ Sub-component/Activity | Indicators |  | Unit | Unit Cost (INR in Lakhs) | Fianl AWPB for 2016-17 |  | Achievement | Target |  |  |  | Achievement |  |  |  | Remarks | Funding Source
|  |  | Apprisal | RIMS |  |  | No of units | Total (INR in Lakhs) | Total (INR in Lakhs) | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 0 | % IFAD | %GoO | %Benificiary | Total
10000 | 1 | Component 1: Community Empowerment | [5 empty] | 378.57
11000 | 1.1 | Sub- Component 1.1: Community Institutions Development | [5 empty] | 368.07 | [10 empty] | 60% | 40% | 0% | 100%
11100 | 1 | Service provider contracts (NGO) | No. FNGO to be engaged |  | MPA | 18.34 | 17 | 311.83
11110 | 1A | Engagement of the MPWs | No. of MPWs engaged |  | pers_month | 0.045 | 0 | 0
11200 | 2 | PMU & MPA Staff Exposure and Training | Programme concept & orientation, Exposure vist of PMU & MPA staffs |  | pers_days | 0.12 | 388 | 16.8
11300 | 3 | NGO staff Exposure and Training | Capacity building of ToTs (NGO Staff ) |  | pers_days | 0.07 | 221 | 5.27
11400 | 4 | CRP training | Capacity building of CRP s By ToTs) |  | pers_days | 0.01 | 1360 | 3.32
11500 | 5 | TOT Training module | RNGO to be engaged for Capacity Building & traing to TOT on 4 different modules |  | pers_MPA/person/session | 2.43 | 1226 | 22.73
11600 | 6 | Training VDA & VDC members on Perparation DVP | One adult male & female member from every HH in VDA and 2(males & females) in VDC. |  | Village | 0.03 | 1082 | 8.12
11700 | 7 | Entry point interventions | One common activity per village identified by VDA / VDC |  | Village | 1.75 | 0 | 0
12000 | 1.2 | Sub- Component 1.2: Stregthening SHGs and Rural Finance | [5 empty] | 10.5 | [10 empty] | 90.4% | 9.6% | 0% | 100%
12100 | 1 | SHG formation & strengthening | Formation and strengthening of SHG, with Maping,audit & supply of materials |  |  | 0.12 | 0 | 0
12200 | 2 | TOT to NGO staff including CRPs
12210 | 2A | SHG functioning, Training on financial literacy and gender | Training of CRPs ,SHG members &Village volunters |  | batch, per CRP and per person | 2.57 | 14 | 10.5
12300 | 3 | Rural Finance
12310 | 3A | Capacity building of GPLF |  |  |  | 1.54 | 0 | 0
12320 | 3B | Funding support to SHG | Pro-poor Fund, VRF1st & 2nd instalment & CIF 1st Instlment |  | member/ GPLF | 1.28 | 0 | 0
12330 | 3C | Pilot on women cooperative | Fisibility study and exposure visit with filling of the gaps |  | study/ per person /per year | 11.41 | 0 | 0
12400 | 4 | Nutrition and social issues
12410 | 4A | Dal Poshak banks | Training to CRPs & SHGs and dal bank equipment |  | Per SHG | 0.075 | 0 | 0
12420 | 4B | Marriage incentives /m | Late marriage incentives to girls |  | person | 0.02 | 0
20000 | 2 | Component 2: Natural Resources mangementa nd Livelihood Improvemnet | [5 empty] | 20.1
21000 | 2.1 | Sub- Component 2.1: Natural Resource Management | [5 empty] | 10.1 | [10 empty] | 56.2% | 35.2% | 8.7% | 100.1%
21100 | 1 | Agriculture Training /a | Training on Cereal crops SRI for rice, millet, Pulses, oilseeds, tuber crops, Horticulture |  | person | 0.01 | 0 | 0
21200 | 2 | Land Rights Allocation: RNGO /e | Training,workshop, review meetings, Identification of the Landless, mapping land allocation HR costs- field level & RNGO level |  | LS |  |  | 10.1
21300 | 3 | Natural Resource Management | Land treatment, Irrigation structures, Horticulture plantation, Cereal / millets crops development & Pulses, oilseeds, tubers development |  | Ha/Structure/ village | 10.1 | 0 | 0
22000 | 2.2 | Sub- Component 2.2. Food and Nutrition Security | [5 empty] | 10 | [10 empty] | 17.4% | 82.6% | 0% | 100%
22100 | 1 | Food security
22110 | 1A | PTG Food production system | Farmers training, Onfarm demonstrations, Seed Production support & Compost-making |  | person/village/SHG | 0.25 | 0 | 0
22120 | 1B | Farmers Field Schools, FFS | Formation/organisation of FFS & capacity building |  | FFS | 0.03 | 0 | 0
22130 | 1C | Research and development support | R&D support on crop varities (OUAT) & Farmer-led crop trials |  | LS/Farmer | 75.1 | 0 | 0
22200 | 2 | Nutrition security
22210 | 2A | Nutrition-dense crop diversification | Nutrition needs & use assessment , nutrient value of uncultivated & foodsHousehold crop development |  | Study/ Farmers | 10.03 | 0 | 10
22220 | 2B | Health camps /h | Health Camps at GP level |  | GP | 0.125 | 0 | 0
23000 | 2.3 | Sub- Component 2.3: Livelihoods Improvement | [5 empty] | 0 | [10 empty] | 13.9% | 80.2% | 5.9% | 100%
23100 | 1 | Training CSP | Training to CSPs on Agriculture and horticulture,Livestock & IGA activity |  | per_CSP_perday | 0.015 | 0 | 0
23200 | 2 | Support to CSP for upscaling | [5 empty] | 0
| 2A | Crop diversification | Support for Crops diversification |  | CSP | 0.03 | 0
| 2B | Ktchen garden | Support for Kitchen garden |  | CSP | 0.05 | 0 | 0
| 2C | Horticulture | Support for horticulture |  | CSP | 1.17 | 0 | 0
23300 | 3 | Livestock demonstrations | [5 empty] | 0
| 3A | Poultry (Mother chick) | Poultry mother units |  | CSP | 2 | 0
| 3B | Goat rearing | Goat rearing |  | CSP | 0.3 | 0 | 0
| 3C | Animal health camp | Animal health camp on MPA level |  | MPA | 0.5 | 0 | 0
23400 | 4 | Household production support | Kitchen garden, Goat rearing, Backyard Poultry and IGA activity |  |  |  | 0
| 4A | Kitchen garden | Support to HH for Kitchen garden |  | household | 0.02 | 0 | 0
| 4B | Backyard poultry | Support to HH for Backyard Poultry |  | household | 0.03 | 0 | 0
| 4C | Goat rearing | Support to HH for Goat rearing |  | household | 0.3 | 0 | 0
| 4D | IGA (non-farm) | Support to HH for IGA activity |  | household | 0.3 | 0 | 0
23500 | 5 | Setting up of Producers Collectives | feasibility report, LRA for producer collectives,promotion of livelihood collectives and Ifrastructure and hand holding support |  | Study/per Collective | 21.5 | 0 | 0
23600 | 6 | Support for NTFP marketing | Support to SHG on NTFP collection and Haat bazar development |  | Per GP/Per MPA | 28 | 0 | 0
23700 | 7 | Vocational Training /l | Vocational training to youth. |  | person | 0.3 | 0 | 0
30000 | 3 | Component 3: Community Infrastructure and Drudgery reduction. | [5 empty] | 0
31000 | 3.1 | Sub- Component 3.1: Community Infrastructure | [5 empty] | 0 | [10 empty] | 97.1% | 2.7% | 0.2% | 100%
31100 | 1 | Survey, preparation of feasibility reports | Feasibility study for Micro Hydro projects. |  | Study per GP | 5 | 0 | 0
31200 | 2 | Drinking water & sanitation | Drinking water supply with sanitaion |  | each /MPA | 10.4 | 0 | 0
31300 | 3 | Housing & habitat development | CC roads in villages and supply of house/ housing material to HHs |  | each/KM | 6.4 | 0 | 0
31400 | 4 | Roads, electricity & solar lighting | Connecting roads, black-topped, Foot paths, Grid connection & Community solar lighting |  | KM/Each | 61 | 0 | 0
31500 | 5 | Social infrastructure | Multi-purpose community hall,Primary Schools & School toilets |  | each | 16 | 0 | 0
31600 | 6 | Economic Infrastructure | Drying yards, Market yards , Aggregation centres & SHG worksheds |  | each | 14 | 0 | 0
31700 | 7 | Agricultural machinery & tools /b | Power tillers & Seed storage bins |  | set/each | 1.735 | 0
32000 | 3.2 | Sub- Component 3.2: Drudgery Reduction | [16 empty] | 15.2% | 80% | 4.8% | 100%
32100 | 1 | Drugery reduction interventions | Smokeless wood stoves, Solar lanterns, Community Fuelwood reserves & Milling units for millets, rice |  | each/Village | 3.27 | 0 | 0
32200 | 2 | Tribal culture and values | Support to cultural festivals ,Community halls ,Youth dormentary & Sacred Fencing |  | GP/LS/Village | 2.55 | 0 | 0
32300 | 3 | Policy initiatives | Studies, surveys & Legal Advocacy |  | MPA/LS | 3 | 0 | 0
40000 | 4 | Components 4: Programme Management | [5 empty] | 701.24 | 7.3312
41000 | 4.1 | Sub- Component 4.1. Project Management Unit | [5 empty] | 220.06 | 7.2606 | [9 empty] | 42.2% | 57.8% | 0% | 100%
41100 | A | Vehicles | Office equipments for PMU |  | each/ Ls | 8.62 | 6 | 4.8 | 0.11204
41200 | B | Equipment |  |  |  | 18.98 | 81 | 26.85 | 0.104
41300 | C | Surveys, audits and TA
41310 | C.i | Surveys and studies | Baseline survey, RIMS baseline, MTR and endline, Annual outcome survey, MTR survey. PCR study &Other studies |  | survey/study | 150 | 1 | 80
41320 | C.ii | Audits | Internal audit,Statutory audits,Preparation of Finance Manual & Tally software |  | LS | 13 | 2 | 5.5
41330 | C.iii | Technical assistance | National consultants, Staff & NGO recruitment expenses |  | LS/ per month | 8 | 3 | 8 | 0.04
41400 | D | Staff Salary and Allowances
41410 | D.i | Staff salary | Salary for PMU staffs |  | Per_month | 8.1 | 128 | 56 | 6.83
41420 | D.ii | Staff Allowances |  |  |  | 2.51 | 32 | 20.05 | [9 empty] | As PIM has not approved by Govt.
41500 | E | Office operating costs | Operating cost for PMU |  | Per_month | 6.69 | 47.7 | 18.86 | 0.17452
42000 | 4.2 | Sub- Component 4.2: Micro-Project Agency Unit | [5 empty] | 461.98 | 0 | [9 empty] | 60.2% | 39.8% | 0% | 100%
41100 | A | Vehicles | Office equipments for MPAs |  | each/ Ls | 7.81 | 85 | 21.25
41200 | B | Equipment |  |  |  | 9.53 | 408 | 124.1
41300 | C | Surveys, audits and TA
| C.i | Survey |  |  |  | 0
41320 | C.ii | Audits | Internal audit &Statutory audits |  | per_year | 1.5 | 17 | 5.1
41330 | C.iii | TA Asst Engineers (Degree-holders) /d | TA Asst Engineers (Degree-holders) |  | per_person_per day | 0.025 | 0 | 0
41400 | D | Staff Salary and Allowances
41410 | D.i | Staff salary
|  | Regular cadre staff | Salary for MPAs staffs |  | Per_month | 3.2 | 490 | 197
|  | Contractual staff | Salary for MPAs staffs |  | Per_month | 0.55 | 288 | 30.27
41420 | D.ii | Staff Allowances
|  | Regular cadre staff |  |  |  | 0.56 | 190 | 34.05
|  | Contractual staff |  |  |  | 0.6 | 110 | 24.2
41500 | E | Office operating costs | Operating cost for MPAs |  | Per_month | 1.42 | 476 | 26.01
41600 | F | Construction and Renovation of Buildings |  |  | each | 38.35 | 0 | 0
43000 | 4.3 | Sub- Component 4.3: Monitoring and evaluation and KM | [5 empty] | 19.2 | 0.07059 | [9 empty] | 20% | 80% | 0% | 100%
43100 | 1 | Start up workshop | Start up workshop at state and MPA level |  | event | 4.25 | 18 | 8.25
43200 | 2 | Monthly review meetings | Monthly review meetings at state and MPA level |  | meeting | 0.225 | 108 | 3.75 | 0.07059
43300 | 3 | Learning and sharing workshop | Quality workshop at GP, MPA and PMU level |  | each | 0.6 | 84 | 4.2
43400 | 4 | Review workshop | MTR & PCR review workshop |  | LS | 5.5 | 0 | 0
43500 | 5 | Training | Training on RIMS, M&E at state & MPA level, annual survey & KAPS training |  | LS | 5 | 2 | 2
41330 | 6 | Technical assistance | MIS design and support, PME consultant and M&E consultant |  | Ls/per month | 44.45 | 1 | 1
43600 | 7 | Concurrent monitoring by external Agency | Concurrent monitoring |  | MPA | 0.35 | 0 | 0
|  | Grand Total | [5 empty] | 1099.91 | 7.3312
Details are in Annexure-I
NB:
PMU level staffs for 8 months
MPA level staffs for 5 months
NGO level staffs for 5 months
MPWs for GP for 4 months
Monthly review meeting for 4months

## Annexure
Annexure-I (INR in Lakhs)
Code & Sub Code | Annual Work Plan Budget of OPELIP for the year 2016-17
| Sl No. | Component, Sub-component & Activities | Unit |  | AWPB for 2016-17 |  | Proposed for Deduction* | Final AWPB 2016-17 | Achievement
|  |  | Unit | Unit Cost (INR in Lakhs) | No of units | Total |  |  | Total (INR in Lakhs)
10000 | 1 | Component 1: Community Empowerment |  |  |  | 1136.7975 | 758.2275 | 378.555 | 0
11000 | 1.1 | Sub- Component 1.1:Community Institutions Development |  |  |  | 1083.8975 | 715.8275 | 368.055 | 0
11100 | 1 | Service provider contracts (NGO)
|  | Year 1 (Five Months) | MPA | 30.57 | 17 | 519.69 | 207.86 | 311.83
|  | Year 2 /a | MPA | 70.47 | 0 | 0 |  | 0
|  | Year 3 | MPA | 70.47 | 0 | 0 |  | 0
|  | Year 4 | MPA | 70.47 | 0 | 0 |  | 0
|  | Year 5 | MPA | 68.1075 | 0 | 0 |  | 0
|  | Year 6 | MPA | 61.02 | 0 | 0 |  | 0
|  | Year 7 | MPA | 9.2475 | 0 | 0 |  | 0
|  | Year 8 | MPA | 0 | 0 | 0 |  | 0
11110 | 1A | Wages to MPWs(Multi purpose Worker) /b | pers_month | 0.045 |  | 14.4 | 14.4 | 0
|  | Subtotal Service provider contracts (NGO) |  |  |  | 534.09 | 222.26 | 311.83 | 0
11200 | 2 | PMU & MPA Staff Exposure and Training
11210 | i | Exposure visits- 7 days /c | pers_days | 0.075 | 183 | 16.05 | 2.32 | 13.725
11220 | ii | Nutrition & gender training /d | pers_days | 0.015 | 36 | 0.54 |  | 0.54
11230 | ii | Training for Junior engineers /e | pers_days | 0.015 | 72 | 1.785 | 0.705 | 1.08
11240 | iv | Programme concept & orientation /f | pers_days | 0.015 | 97 | 1.635 | 0.18 | 1.455
|  | PMU & MPA Staff Exposure and Training |  |  |  | 20.01 | 3.205 | 16.8 | 0
11300 | 3 | NGO staff Exposure and Training
11210 | i | Exposure visits /g | pers_days | 0.05 | 85 | 8.5 | 4.25 | 4.25
11220 | ii | Nutrition & Gender training /h | pers_days | 0.0075 | 34 | 0.51 | 0.25 | 0.255
11240 | iii | Programme concept & orientation /i | pers_days | 0.0075 | 68 | 0.51 |  | 0.51
11250 | iv | NRM training 4 pers for 2 days | pers_days | 0.0075 | 34 | 0.51 | 0.25 | 0.255
|  | NGO staff Exposure and Training |  |  |  | 10.03 | 4.75 | 5.27 | 0
11400 | 4 | CRP training
11240 | i | Programme concept & orientation /j | persons | 0.0015 | 510 | 0.765 |  | 0.765
11410 | ii | Community mobilisation, health & nutrition /k | person | 0.003 | 340 | 1.02 |  | 1.02
11420 | iii | VDP prepartion and book-keeping /l | person | 0.003 | 510 | 1.53 |  | 1.53
|  | Subtotal CRP training |  |  |  | 3.315 | 0 | 3.315 | 0
11500 | 5 | TOT Training module
11510 | 5A | Hygeine & management of common diseases |  |  |  | 11.3625 |  | 11.3625
| i | Resource Agency cost for TOT | pers_MPA | 0.5 | 17 | 8.5 |  | 8.5
| ii | Training arrangement | persons | 0.005 | 510 | 2.55 |  | 2.55
| iii | Training materials | LS | 0.1 | 1 | 0.1 |  | 0.1
| iv | Honorarium to the tranlator | session | 0.0025 | 85 | 0.2125 |  | 0.2125
|  | Subtotal Hygeine & management of common diseases |  |  |  | 11.3625 | 0 | 11.3625 | 0
11520 | 5B | Life skills education for girrls
| i | Resource Agency cost for TOT | pers_MPA | 0.5 |  | 8.5 | 8.5
| ii | Training arrangement | persons | 0.005 |  | 2.55 | 2.55
| iii | Training materials | LS | 0.1 |  | 0.1 | 0.1
| iv | Honorarium to the tranlator | session | 0.0025 |  | 0.2125 | 0.2125
|  | Subtotal Life skills education for girls |  |  |  | 11.3625 | 11.3625 | 0 | 0
11530 | 5C | Women sexual and reproduction health
| i | Resource Agency cost for TOT | pers_MPA | 0.5 | 0 | 0 |  | 0
| ii | Training arrangement | persons | 0.005 | 0 | 0 |  | 0
| iii | Training materials | LS | 0.1 | 0 | 0 |  | 0
| iv | Honorarium to the tranlator | session | 0.0025 | 0 | 0 |  | 0
|  | Subtotal Women sexual and reproduction health |  |  |  | 0 | 0 | 0 | 0
11540 | 5D | Confronting malaria
| i | Resource Agency cost for TOT | pers_MPA | 0.5 | 17 | 8.5 |  | 8.5
| ii | Training arrangement | persons | 0.005 | 510 | 2.55 |  | 2.55
| iii | Training materials | LS | 0.1 | 1 | 0.1 |  | 0.1
| iv | Honorarium to the tranlator | session | 0.0025 | 85 | 0.2125 |  | 0.2125
|  | Subtotal Confronting malaria |  |  |  | 11.3625 | 0 | 11.3625 | 0
|  | Subtotal TOT Training module |  |  |  | 34.0875 | 11.3625 | 22.725 | 0
11600 | 6 | Training VDA & VDC members on preparation of VDP
11610 | 6A | VDP preparation training /m | village | 0.0075 | 541 | 4.0575 |  | 4.0575
11620 | 6B | AWPB preparation training /n | village | 0.0075 | 0 | 0 |  | 0
11630 | 6C | Book-keeping training /o | village | 0.0075 | 541 | 4.0575 |  | 4.0575
11640 | 6D | Audit of accounts | village | 0.005 | 0 | 0 |  | 0
|  | Subtotal Training VDA members |  |  |  | 8.115 | 0 | 8.115 | 0
11700 | 7 | Entry point interventions(EPI) | village | 1.75 |  | 474.25 | 474.25
|  | Subtotal Village development(EPI) |  |  |  | 474.25 | 474.25 | 0 | 0
12000 | 1.2 | Sub- Component 1.2: Stregthening SHGs and Rural Finance |  |  |  | 52.9 | 42.4 | 10.5 | 0
12100 | 1 | SHG formation & strengthening
12110 | 1A | SHG mapping,audit & accounts |  |  |  | 0 |  | 0
| i | SHG mapping, audit etc | SHG | 0.005 | 0 | 0 |  | 0
| ii | Thematic exposure visits /a | SHG | 0.1 | 0 | 0 |  | 0
|  | Subtotal SHG mapping,audit & accounts |  |  |  | 0 |  | 0 | 0
12120 | 1B | SHG equipment: A/c books, Safe & calculators | SHG | 0.0195 | 0 | 0 |  | 0
|  | Subtotal SHG formation & strengthening |  |  |  | 0 | 0 | 0 | 0
12200 | 2 | TOT to NGO staff including CRPs
12210 | 2A | SHG functioning |  |  |  | 5.25 |  | 5.25
| i | Resource agency cost for TOT /b | batch | 0.75 | 7 | 5.25 |  | 5.25
| ii | Training of CRPs 6 days | CRP_day | 0.03 | 0 | 0 |  | 0
| iii | Training SHG members | persons | 0.0035 | 0 | 0 |  | 0
| iv | Training Leaders for 2 days | persons | 0.007 | 0 | 0 |  | 0
| v | Training book-keepers, 2 days | persons | 0.007 | 0 | 0 |  | 0
|  | Subtotal SHG functioning |  |  |  | 5.25 | 0 | 5.25 | 0
12220 | 2B | Financial literacy, with 6 modules
| i | Resource agency cost for TOT /c | batch | 0.75 | 7 | 5.25 |  | 5.25
| ii | Training of CRPs 4 days | CRP | 0.02 | 0 | 0 |  | 0
| iii | Training SHG members | persons | 0.0035 | 0 | 0 |  | 0
| iv | Training materials | LS | 1 | 0 | 0 |  | 0
|  | Subtotal Financial literacy, with 6 modules |  |  |  | 5.25 | 0 | 5.25 | 0
12230 | 2C | Gender training
| i | Resource agency cost for TOT /d | persons | 0.5 | 0 | 7 | 7
| ii | Village volunteers /e | persons | 0.03 | 0 | 0 |  | 0
| iii | Training CRPs | persons | 0.0035 | 0 | 0 |  | 0
|  | Subtotal Gender training |  |  |  | 7 | 7 | 0 | 0
|  | Subtotal TOT to NGO staff including CRPs |  |  |  | 17.5 | 7 | 10.5 | 0
12300 | 3 | Rural Finance
12310 | 3A | Capacity building of GPLF /f |  |  |  | 35.4 |  | 0
| i | MIS support to MPA | Lumpsum | 0.6 | 0 | 10.2 | 10.2
| ii | GPLF building & strenthening |  |  |  | 25.2 |  | 0
| a | Training on leadership & governance /g | person | 0.01 | 0 | 0 |  | 0
| b | Accounting training-2 days /h | person | 0.01 | 0 | 0 |  | 0
| c | Start up funds for furniture, bicycles etc | GPLF | 0.5 | 0 | 0 |  | 0
| d | Annual general body meeting | GPLF | 0.05 | 0 | 0 |  | 0
| e | Mobility expenses | LS | 0.025 | 0 | 0 |  | 0
| f | CRP salary | pers_month | 0.045 | 0 | 0 |  | 0
| g | Operating costs to GPLF (honorarium to members) | GPLF | 0.3 | 0 | 25.2
|  | Subtotal GPLF building & strenthening |  |  |  | 25.2 | 25.2 | 0 | 0
|  | Subtotal Capacity building of GPLF |  |  |  | 35.4 | 35.4 | 0 | 0
12320 | 3B | Funding support to SHG
| i | Pro-poor Fund first instalment | member | 0.005 | 0 | 0 |  | 0
| ii | Pro-poor fund 2nd instalment | member | 0.005 | 0 | 0 |  | 0
| iii | VRF 1st & 2nd instalments/i | GPLF | 0.5 | 0 | 0 |  | 0
| iv | VRF 3rd and 4th instalments | GPLF | 0.75 | 0 | 0 |  | 0
| v | CIF first instalment /j | member | 0.022 | 0 | 0 |  | 0
|  | Subtotal Funding support to SHG |  |  |  | 0 | 0 | 0 | 0
12330 | 3C | Pilot on women cooperative
| i | Feasibility study /k | study | 5 | 0 | 0 |  | 0 | 0
| ii | Exposure visits (in country) | persons | 0.05 | 0 | 0 |  | 0 | 0
| iii | Viability gap expenses | year | 5 | 0 | 0 |  | 0 | 0
| iv | Equipment & computer | LS | 0.75 | 0 | 0 |  | 0 | 0
| v | Staff training on cooperatives | person | 0.025 | 0 | 0 |  | 0 | 0
| vi | Training on governance & responsibilities | LS | 0.025 | 0 | 0 |  | 0 | 0
| vii | Legal assistance | LS | 0.03 | 0 | 0 |  | 0 | 0
| viii | Training on accounting & book-keeping | LS | 0.03 | 0 | 0 |  | 0 | 0
| ix | TA for hand-holding | year | 0.5 | 0 | 0 |  | 0 | 0
|  | Subtotal Pilot on women cooperative |  |  |  | 0 | 0 | 0 | 0
|  | Subtotal Rural Finance |  |  |  | 35.4 | 35.4 | 0 | 0
12400 | 4 | Nutrition and social issues
12410 | 4A | Dal Poshak banks |  |  |  | 0 |  | 0
| i | Training CRPs and SHG | LS | 0.0025 | 0 | 0 |  | 0
| ii | Dal Bank equipment /l | SHG | 0.02 | 0 | 0 |  | 0
| iii | Supply of Dal /m | SHG | 0.0525 | 0 | 0 |  | 0
|  | Subtotal Dal Poshak banks |  |  |  | 0 | 0 | 0 | 0
12420 | 4B | Marriage incentives /n |  |  |  | 0 |  | 0
| i | Late marriage incentives to girls | person | 0.02 | 0 | 0 |  | 0
|  | SubtotalMarriage incentives |  |  |  | 0 | 0 | 0 | 0
|  | Subtotal Nutrition and social issues |  |  |  | 0 | 0 | 0 | 0
20000 | 2 | Component 2: Natural Resources mangementa nd Livelihood Improvemnet |  |  |  | 290.5513 | 270.45 | 20.1 | 0
21000 | 2.1 | Sub- Component 2.1: Natural Resource Management |  |  |  | 238.1013 | 228 | 10.1 | 0
21100 | 1 | Agriculture Training /a
| 1A | Cereal crops SRI for rice, millet /b | person | 0.0015 | 0 | 0 |  | 0 | 0
| 1B | Pulses, oilseeds, tuber crops /c | person | 0.0015 | 0 | 0 |  | 0 | 0
| 1C | Horticulture /d | person | 0.0045 | 0 | 0 |  | 0 | 0
|  | Subtotal Agriculture Training |  |  |  | 0 | 0 | 0 | 0
21200 | 2 | Land Rights Allocation: RNGO /e
| 2A | Training,workshop, review meetings /f | lumpsum |  |  | 20.13 | 10.03 | 10.1
| 2B | Identification of the Landless, mapping land allocation | lumpsum |  |  | 90.2833 | 90.28
| 2C | Human resources costs- field level | lumpsum |  |  | 55.74 | 55.74
| 2D | Human resources costs, For RNGO | lumpsum |  |  | 22.248 | 22.25
| 2E | RNGO Management cost | lumpsum |  |  | 49.7 | 49.7
|  | Subtotal Land Rights Allocation: RNGO |  |  |  | 238.1013 | 228 | 10.1 | 0
21300 | 3 | Natural Resource Management
21310 | 3A | Land treatment /g | ha | 0.2 | 0 | 0 |  | 0
21320 | 3B | Irrigation structures /h | structure | 4 | 0 | 0 |  | 0
21330 | 3C | Horticulture plantation /i | village | 5 | 0 | 0 |  | 0
21340 | 3D | Cereal / millets crops development /j | village | 0.4 | 0 | 0 |  | 0
21350 | 3E | Pulses, oilseeds, tubers development /k | village | 0.5 | 0 | 0 |  | 0
|  | Subtotal Natural Resource Management |  |  |  | 0 | 0 | 0 | 0
22000 | 2.2 | Sub- Component 2.2: Food and Nutrition Security |  |  |  | 31 | 21 | 10 | 0
22100 | 1 | Food security
22110 | 1A | PTG Food production system |  |  |  | 0 |  | 0
22111 | i | Farmers training /a | person | 0 | 0 | 0 |  | 0
22112 | ii | Onfarm demonstrations | village | 0.1 | 0 | 0 |  | 0
22113 | iii | Seed Production support /b | SHG | 0.1 | 0 | 0 |  | 0
22114 | iv | Compost-making /c | SHG | 0.05 | 0 | 0 |  | 0
|  | Subtotal PTG Food production system |  |  |  | 0 | 0 | 0 | 0
22120 | 1B | Farmers Field Schools, FFS
| i | Formation/organisation of FFS /d | FSS | 0.01 | 0 | 0 |  | 0
| ii | Capacity building | FFS | 0.02 | 0 | 0 |  | 0
|  | Subtotal Farmers Field Schools, FFS |  |  |  | 0 | 0 | 0 | 0
22130 | 1C | Research and development support
| i | R&D support on crop varities (OUAT) /e | LS | 75 | 0 | 0 |  | 0
| ii | Farmer-led crop trials /f | farmers | 0.1 | 0 | 0 |  | 0
|  | Subtotal Research and development support |  |  |  | 0 | 0 | 0 | 0
|  | Subtotal Food security |  |  |  | 0 | 0 | 0 | 0
22200 | 2 | Nutrition security
22210 | 2A | Nutrition-dense crop diversification |  |  |  | 10 |  | 10
| i | Nutrition needs assessment | study | 5 | 1 | 5 |  | 5
| ii | Assessment of use and nutrient value of uncultivated foods | study | 5 | 1 | 5 |  | 5
| iii | Household crop development /g | farmers | 0.025 | 0 | 0 |  | 0
|  | Subtotal Nutrition-dense crop diversification |  |  |  | 10 | 0 | 10 | 0
22220 | 2B | Health camps /h | GP | 0.125 | 0 | 21 | 21
|  | Subtotal Health camps |  |  |  | 21 | 21 | 0 | 0
|  | Subtotal Nutrition security |  |  |  | 31 | 21 | 10 | 0
23000 | 2.3 | Sub- Component 2.3: Livelihoods Improvement |  |  |  | 21.45 | 21.45 | 0 | 0
23100 | 1 | Training Community Service Provider(CSP)
| 1A | Agriculture and horticulture training /a | CSP | 0.005 |  | 6 | 6
| 1B | Livestock training /b | pers_day | 0.005 |  | 9.45 | 9.45
| 1C | IGA training | CSP | 0.005 |  | 6 | 6
|  | Subtotal Training CSP |  |  |  | 21.45 | 21.45 | 0 | 0
23200 | 2 | Support to CSPs in upscaling
| 2A | Support for Crops diversification /c | CSP | 0.03 | 0 | 0 |  | 0
| 2B | Support for Kitchen garden /d | CSP | 0.05 | 0 | 0 |  | 0
| 2C | Support for horticulture 1st year /e | CSP | 0.17 | 0 | 0 |  | 0
| 2D | Support for horticulture 2nd year | CSP | 0.7 | 0 | 0 |  | 0
| 2E | Support for horticulture 3rd year | CSP | 0.3 | 0 | 0 |  | 0
|  | Subtotal Support to CSPs in upscaling |  |  |  | 0 | 0 | 0 | 0
23300 | 3 | Livestock demonstrations
| 3A | Poultry mother units /f | CSP | 2 | 0 | 0 |  | 0
| 3B | Goat rearing unit (5+1) including shed | CSP | 0.3 | 0 | 0 |  | 0
| 3C | Animal health camps /g | MPA | 0.5 | 0 | 0 |  | 0
|  | Subtotal Livestock demonstrations |  |  |  | 0 | 0 | 0 | 0
23400 | 4 | Household production support
| 4A | Kitchen gardens /h | household | 0.02 | 0 | 0 |  | 0
| 4B | Backyard Poultry (10 bird unit) | household | 0.03 | 0 | 0 |  | 0
| 4C | Goat rearing unit (5 does+1 buck) | household | 0.3 | 0 | 0 |  | 0
| 4D | IGA units /i | household | 0.3 | 0 | 0 |  | 0
|  | Subtotal Household production support |  |  |  | 0 | 0 | 0 | 0
23500 | 5 | Setting up of Producers Collectives
23510 | 5A | Preparation of Feasibility Reports | per MPA | 1 | 0 | 0 |  | 0
23520 | 5B.i | LRA for Producer collectives | Collective | 7.5 | 0 | 0 |  | 0
| ii | Promotion of Livelihoods collectives | collective | 4 | 0 | 0 |  | 0
| iii | Infrastructure and equipment | Collective | 8 | 0 | 0 |  | 0
| iv | Hand-holding facilities | Collective | 1 | 0 | 0 |  | 0
|  | Subtotal Setting up of Producers Collectives |  |  |  | 0 | 0 | 0 | 0
23600 | 6 | Support for NTFP marketing
23610 | 6A | Support for SHG,equipment for NTFP collection /j | per GP | 3 | 0 | 0 |  | 0
23620 | 6B | Haat bazar development for NTFP aggregation /k | per MPA | 25 | 0 | 0 |  | 0
|  | Subtotal Support for NTFP marketing |  |  |  | 0 | 0 | 0 | 0
23700 | 7 | Vocational Training /l | person | 0.3 | 0 | 0 |  | 0
|  | Subtotal Vocational Training |  |  |  | 0 | 0 | 0 | 0
30000 | 3 | Component 3: Community Infrastructure and Drudgery reduction. |  |  |  | 89.25 | 89.25 | 0 | 0
31000 | 3.1 | Sub- Component 3.1: Community Infrastructure |  |  |  | 89.25 | 89.25 | 0 | 0
31100 | 1 | Survey, preparation of feasibility reports
| 1A | Feasibiltiy studies | GP | 5 | 0 | 0 |  | 0
| 1B | feasibility studies for micro-hydel | GP | 0 | 44 | 0 |  | 0
|  | Subtotal Survey, preparation of feasibility reports |  |  |  | 0 |  | 0 | 0
31200 | 2 | Drinking water & sanitation |  |  |  | 89.25 |  | 0
31210 | 2A | Gravity water supply | each | 5.25 | 0 | 89.25 | 89.25
31220 | 2B | Hand pumps | each | 1 | 0 | 0 |  | 0
31230 | 2C | Toilets | each | 0.15 | 0 | 0 |  | 0
31240 | 2D | Water Purification pilot | MPA | 4 | 0 | 0 |  | 0
|  | Subtotal Drinking water & sanitation |  |  |  | 89.25 | 89.25 | 0 | 0
31300 | 3 | Housing & habitat development
31310 | 3A.i | Housing units | each | 1 | 0 | 0 |  | 0
| 3A.ii | Construction materials for house improvement | each | 0.4 | 0 | 0 |  | 0
31320 | 3B | CC road in villages /a | km | 5 | 0 | 0 |  | 0
|  | Subtotal Housing & habitat development |  |  |  | 0 | 0 | 0 | 0
31400 | 4 | Roads, electricity & solar lighting
| 4A | Connecting roads, black-topped | km | 40 | 0 | 0 |  | 0
| 4B | Foot paths | km | 10 | 0 | 0 |  | 0
| 4C | Grid connection | km | 10 | 0 | 0 |  | 0
| 4D | Community solar lighting | each | 1 | 0 | 0 |  | 0
|  | Subtotal Roads, electricity & solar lighting |  |  |  | 0 | 0 | 0 | 0
31500 | 5 | Social infrastructure
| 5A | Multi-purpose community hall | each | 5 | 0 | 0 |  | 0
| 5B | Primary Schools | each | 10 | 0 | 0 |  | 0
| 5C | School toilets | each | 1 | 0 | 0 |  | 0
|  | Subtotal Social infrastructure |  |  |  | 0 | 0 | 0 | 0
31600 | 6 | Economic Infrastructure
| 6A | Drying yards | each | 2 | 0 | 0 |  | 0
| 6B | Market yards | each | 5 | 0 | 0 |  | 0
| 6C | Aggregation centres | each | 4 | 0 | 0 |  | 0
| 6D | SHG worksheds | each | 3 | 0 | 0 |  | 0
|  | Subtotal Economic Infrastructure |  |  |  | 0 | 0 | 0 | 0
31700 | 7 | Agricultural machinery & tools /b
| 7A | Power tillers /c | set | 1.735 | 0 | 0 |  | 0
| 7B | Seed storage bins | each | 0.0035 | 0 | 0 |  | 0
|  | Subtotal Agricultural machinery & tools |  |  |  | 0 | 0 | 0 | 0
32000 | 3.2 | Sub- Component 3.2: Drudgery Reduction |  |  |  | 0 | 0 | 0 | 0
32100 | 1 | Drugery reduction interventions
| 1A | Smokeless wood stoves | each | 0.015 | 0 | 0 |  | 0
| 1B | Solar lanterns | each | 0.05 | 0 | 0 |  | 0
| 1C | Community Fuelwood reserves /a | village | 0.2 | 0 | 0 |  | 0
| 1D | Milling units for millets, rice /b | each | 3 | 0 | 0 |  | 0
|  | Subtotal Drugery reduction interventions |  |  |  | 0 | 0 | 0 | 0
32200 | 2 | Tribal culture and values
| 2A | Support to cultural festivals /c | GP | 0.5 | 0 | 0 |  | 0
| 2B | Community halls /d | GP |  | 0 | 0 |  | 0
| 2C | Youth dormentary | LS | 2 | 0 | 0 |  | 0
| 2D | Sacred Fencing /e | village | 0.05 | 0 | 0 |  | 0
|  | Subtotal Tribal culture and values |  |  |  | 0 | 0 | 0 | 0
32300 | 3 | Policy initiatives
| 3A | Studies and surveys | MPA | 1 | 0 | 0 |  | 0
| 3B | Legal Advocacy | LS | 2 | 0 | 0 |  | 0
|  | Subtotal Policy initiatives |  |  |  | 0 | 0 | 0 | 0
40000 | 4 | Components 4 Programme Management |  |  |  | 1059.355 | 358.118 | 701.242 | 7.3322
41000 | 4.1 | Sub- Component 4.1: Project Management Unit |  |  |  | 303.58 | 83.52 | 220.06 | 7.2616
41100 | A. | Vehicles | [6 empty] | 0.11204
41101 | i | Procurement of Vehicles | Each | 7 | 0 | 0 |  | 0
41102 | ii | Hiring of Vehicles | pers_month | 0.8 | 6 | 6.4 | 1.6 | 4.8 | 0.11204
41103 | iii | Motor Cycles | each | 0.5 | 0 | 0 |  | 0
41104 | iv | POL for Vehicles and Motor Cycles | pers_month | 0.3 | 0 | 0 |  | 0
41105 | v | Maintenance of Vehicles/Motor Cycles etc | per month | 0.02 | 0 | 0 |  | 0
| A | Sub total Vehicles |  |  |  | 6.4 | 1.6 | 4.8 | 0.11204
41200 | B. | Equipments | [6 empty] | 0.104
41201 | i | Computers Laptop | Each | 0.45 | 10 | 4.5 |  | 4.5
41202 | ii | Computer Desktop | Each | 0.35 | 5 | 1.75 |  | 1.75
41203 | iii | Printer,Scaner cum Photocopier (sets) | Each | 0.45 | 3 | 1.35 |  | 1.35
41204 | iv | Printer (Only) | each | 0.075 | 3 | 0.225 |  | 0.225 | 0.104
41205 | v | Scanner | each | 0.075 | 1 | 0.075 |  | 0.075
41206 | vi | Air conditioners | each | 0.4 | 8 | 3.2 |  | 3.2
41207 | vii | Water filters | each | 0.3 | 1 | 0.3 |  | 0.3
41208 | viii | Water Coolers | each | 0.12 | 0 | 0 |  | 0
41209 | ix | Ceiling fans | each | 0.035 | 10 | 0.35 |  | 0.35
41210 | x | Genset, silent mode | each | 4 | 0 | 4 | 4 | 0
41211 | xi | Invertors | each | 0.5 | 2 | 1 |  | 1
41212 | xii | Cameras | each | 0.075 | 0 | 0 |  | 0
41213 | xiii | EPBX Box | each | 0.2 | 1 | 0.2 |  | 0.2
41214 | xiv | Fax Machine | each | 0.15 | 1 | 0.15 |  | 0.15
41215 | xv | V sat / Broadband connection | each | 1.5 | 1 | 1.5 |  | 1.5
41216 | xvi | Intercom | each | 0.02 | 10 | 0.2 |  | 0.2
41217 | xvii | Handycam | each | 0.35 | 0 | 0.7 | 0.7 | 0
41218 | xviii | Digital cameras | each | 0.075 | 6 | 0.45 |  | 0.45
41219 | xix | Mobile | each | 0.1 | 11 | 1.1 |  | 1.1
41220 | xx | TV | each | 1 | 1 | 1 |  | 1
41221 | xxi | LCD projector | each | 1.5 | 1 | 1.5 |  | 1.5
41222 | xxii | Other equipment /a | each | 0.25 | 4 | 1 |  | 1
41223 | xxiii | Furniture set | Each | 5 | 1 | 5 |  | 5
41224 | xxiv | Office Renovation | LS | 2 | 1 | 2 |  | 2
|  | Sub total Equipments |  |  |  | 31.55 | 4.7 | 26.85 | 0.104
41300 | C | Surveys, audits and TA
41310 | C.i | 1. Surveys and studies |  |  |  | 110 | 30 | 80
|  | Baseline survey /b | LS | 80 | 1 | 80 |  | 80
|  | RIMS baseline, MTR and endline | survey | 25 | 0 | 25 | 25
|  | Annual outcome survey | survey | 5 | 0 | 5 | 5
|  | MTR survey | survey | 10 | 0 | 0 |  | 0
|  | PCR study | study | 25 | 0 | 0 |  | 0
|  | Other studies | study | 5 | 0 | 0 |  | 0
|  | Subtotal Surveys and studies |  |  |  | 110 | 30 | 80 | 0
41320 | C.ii | Audits |  |  |  | 10.5 |  | 5.5
|  | Internal audit | year | 0.5 | 1 | 0.5 |  | 0.5
|  | Statutory audits | year | 2.5 | 0 | 0 |  | 0
|  | Preparation of Finance Manual /c | lumpsum | 5 | 0 | 5 | 5 | 0
|  | Tally software | lumpsum | 5 | 1 | 5 |  | 5
|  | Subtotal Audits |  |  |  | 10.5 | 5 | 5.5 | 0
41330 | C.iii | Technical assistance |  |  |  | 12 |  | 8
|  | National consultants | pers_month | 2 | 1 | 2 |  | 2
|  | Staff recruitment expenses | LS | 5 | 0 | 5 | 2 | 3 | 0.04
|  | NGO recruitment expenses | LS | 5 | 0 | 5 | 2 | 3
|  | Subtotal Technical assistance |  |  |  | 12 | 4 | 8 | 0.04
|  | Sub total Surveys, audits and TA |  |  |  | 132.5 | 39 | 93.5 | 0.04
41400 | D | Staff Salary and Allowances | [6 empty] | 0
41410 | D.i | Staff salary |  |  |  | 58.4 |  | 56
| a | State Programme Director | pers_month | 1.25 | 8 | 10 |  | 10
| b | Deputy Programme Director | pers_month | 0.75 | 8 | 6 |  | 6
| c | Revenue Officer (Land rights) /d | pers_month | 0.5 | 0 | 0 |  | 0
| d | Senior Engineer | pers_month | 0.5 | 8 | 4 |  | 4
| e | Manager Finance | pers_month | 0.5 | 8 | 4 |  | 4 | 0.89
| f | PO(NRM) | pers_month | 0.5 | 8 | 4 |  | 4 | 0.5
| g | PO( L & C) | pers_month | 0.5 | 8 | 4 |  | 4
| h | PO(CB, Gender &Nutrition) | pers_month | 0.5 | 8 | 4 |  | 4 | 1
| i | Manager ( MIS and M&E) | pers_month | 0.5 | 8 | 4 |  | 4 | 1
| j | PO(CI & RF) | pers_month | 0.5 | 8 | 4 |  | 4 | 0.87
| k | Manager( GIS) | pers_month | 0.5 | 8 | 4 |  | 4 | 0.71
| l | System Analyst | pers_month | 0.25 | 8 | 2 |  | 2 | 0.5
| m | Manager, Communications & KM | pers_month | 0.5 | 0 | 0 |  | 0
| n | Accounts Assistants | pers_month | 0.2 | 16 | 3.2 |  | 3.2 | 0.75489
| o | Project Assistant MIS | pers_month | 0.25 | 0 | 0 |  | 0
| p | Executive Assistants | pers_month | 0.15 | 8 | 1.2 |  | 1.2 | 0.3
| q | Support staff | pers_month | 0.1 | 16 | 1.6 |  | 1.6 | 0.30605
| r | Drivers (supporting stff/ DEO) | pers_month | 0.15 | 0 | 2.4 | 2.4 | 0
|  | Sub total Staff Salary |  |  |  | 58.4 | 2.4 | 56 | 6.8309
41420 | D.ii | Staff Allowances
| i | Travel allowance | pers_month | 3 | 3.3 | 24 | 14 | 10
| ii | Deputation Allowance | pers_month | 0.45 | 5 | 3.6 | 1.35 | 2.25
| iii | Obligatory provisions /e | pers_month | 1.45 | 4 | 11.6 | 5.8 | 5.8
| iv | Statutory provision(EPF)/f | pers_month | 0.25 | 8 | 2 |  | 2
|  | Sub total Staff Allowances |  |  |  | 41.2 | 21.15 | 20.05 | 0
|  | Sub total Staff Salary & Allowances |  |  |  | 99.6 | 23.55 | 76.05 | 6.8309
41500 | E | Office operating costs
41501 | i | Advertisement / Publicity | LS | 2 |  | 2 |  | 2 | 0.1322
41502 | ii | Books and Periodicals | LS | 0.5 |  | 0.5 |  | 0.5
41503 | iii | Professional & Legal Charges | LS | 0.25 |  | 0.25 |  | 0.25
41504 | iv | Memberships and Subscription | pers_month |  |  | 0 |  | 0
41505 | v | Bank Charges | pers_month | 0.1 | 6 | 0.8 | 0.2 | 0.6
41506 | vi | Rates and Taxes | pers_month | 0.075 | 6 | 0.6 | 0.15 | 0.45
41507 | vii | Printing and Stationery | pers_month | 0.3 | 4 | 2.4 | 1.2 | 1.2
41508 | viii | Postage and Telegram | pers_month | 0.01 | 6 | 0.08 | 0.02 | 0.06 | 0.04242
41509 | ix | Insurance of Assets | LS | 0.1 |  | 0.1 |  | 0.1
41510 | x | Arbitation Charges | LS |  |  | 0 |  | 0
41511 | xi | Hiring of Security Services | pers_month | 0.1 | 12 | 1.2 |  | 1.2
41512 | xii | Hiring of Auxiliary Services | LS |  |  | 0 |  | 0
41513 | xiii | Seminar/Conference | pers_month | 0.1 | 5 | 0.8 | 0.3 | 0.5
41514 | xiv | Office operating expenses | per month | 2 | 4.5 | 16 | 7 | 9
41515 | xv | Utilities | per month | 0.4 | 0 | 2.8 | 2.8 | 0
41516 | xvi | Office Rent | per month | 0.75 | 4 | 6 | 3 | 3
|  | Sub total Office Operating Costs |  |  |  | 33.53 | 14.67 | 18.86 | 0.17462
42000 | 4.2 | Sub- Component 4.2: Micro-Project Agency Unit |  |  |  | 708.675 | 246.698 | 461.982 | 0
41100 | A. | Vehicles |  |  |  | 55.25 |  | 21.25
41101 | i | Procurement of Vehicles | Each | 7 | 0 | 0 |  | 0
41102 | ii | Hiring of Vehicles | Each | 0.25 | 85 | 21.25 |  | 21.25
41103 | iii | Motor Cycles | Each | 0.5 | 0 | 34 | 34
41104 | iv | POL for Vehicles and Motor Cycles | Each | 0.02 | 0 | 0 |  | 0
41105 | v | Maintenance of Vehicles/Motor Cycles etc | Each | 0.005 | 0 | 0 |  | 0
41106 | vi | Bycycles | Each | 0.03 | 0 | 0 |  | 0
| A | Sub total Vehicles |  |  |  | 55.25 | 34 | 21.25 | 0
41200 | B. | Equipments |  |  |  | 209.1
41201 | i | Computers Laptop | Each | 0.45 | 68 | 30.6 |  | 30.6
41202 | ii | Computer Desktop | Each | 0.35 | 68 | 23.8 |  | 23.8
41203 | iii | Printer,Scaner cum Photocopier (sets) | Each | 0.45 | 17 | 7.65 |  | 7.65
41204 | iv | Printer (Only) | Each | 0.075 | 17 | 1.275 |  | 1.275
41205 | v | Scanner | Each | 0.075 | 0 | 0 |  | 0
41206 | vi | Air conditioners | Each | 0.4 | 0 | 0 |  | 0
41207 | vii | Water filters | Each | 0.3 | 17 | 5.1 |  | 5.1
41208 | viii | Water Coolers | Each | 0.12 | 0 | 0 |  | 0
41209 | ix | Ceiling fans | Each | 0.035 | 85 | 2.975 |  | 2.975
41210 | x | Genset, silent mode | Each | 2 | 0 | 34 | 34 | 0
41211 | xi | Invertors | Each | 0.4 | 34 | 13.6 |  | 13.6
41212 | xii | Cameras | Each | 0.075 | 17 | 1.275 |  | 1.275
41213 | xiii | EPBX Box | each | 0.2 | 0 | 3.4 | 3.4 | 0
41214 | xiv | Fax Machine | each | 0.15 | 17 | 2.55 |  | 2.55
41215 | xv | V sat / Broadband connection | Each | 0.75 | 17 | 12.75 |  | 12.75
41216 | xvi | Intercom | each | 0.02 | 0 | 0 |  | 0
41217 | xvii | Handycam | each | 0.35 | 0 | 0 |  | 0
41218 | xviii | Digital cameras | each | 0.075 | 17 | 1.275 |  | 1.275
41219 | xix | Mobile | each | 0.1 | 0 | 0 |  | 0
41220 | xx | TV | each | 0.25 | 0 | 0 |  | 0
41221 | xxi | LCD projector | each | 0.65 | 0 | 22.1 | 22.1 | 0
41222 | xxii | Other equipment /a | Each | 0.25 | 17 | 4.25 |  | 4.25
41223 | xxiii | Furniture set | Each | 1 | 17 | 25.5 | 8.5 | 17
41224 | xxiv | Office Renovation | Each | 1 | 0 | 17 | 17 | 0
|  | Sub total Equipments |  |  |  | 209.1 | 85 | 124.1 | 0
41300 | C | Surveys, audits and Techinical Assistant(TA) |  |  |  | 14.875 |  | 5.1
| 3.i | Survey and Studies
41320 | 3.ii | Audits |  |  |  | 8.5 |  | 5.1
|  | Internal audit | year | 0.3 | 17 | 8.5 | 3.4 | 5.1
|  | Statutory audits | year | 1 | 0 | 0 |  | 0
|  | Sub total Surveys,Audits |  |  |  | 8.5 | 3.4 | 5.1
41330 | 3.iii | Technical Assistant (Asst Engineers (Degree-holders)) /d | pers_days | 0.025 |  | 6.375 | 6.38 | 0
|  | Sub total TA Asst Engineers |  |  |  | 6.375 | 6.38 | 0
|  | Sub total Surveys, audits and TA |  |  |  | 14.875 | 9.78 | 5.1 | 0
41400 | D | Staff Salary and Allowances
41410 | D.i | Staff salary (Regular)
| a | Special Officer | pers_month | 0.6 | 85 | 51 |  | 51
| b | Junior Engineer (5 Regular) | pers_month | 0.6 | 25 | 15 |  | 15
| c | Junior Agricultural Officer | pers_month | 0.6 | 85 | 51 |  | 51
| d | Senior Clerk or Accountant (6 Regular) | pers_month | 0.3 | 30 | 9 |  | 9
| e | Junier Clerk (Accountants) (10 Regular) | pers_month | 0.3 | 50 | 15 |  | 15
| f | Field Assistant (Nutrition focal point) (9 Regular) | pers_month | 0.3 | 45 | 13.5 |  | 13.5
| g | Drivers | pers_month | 0.3 | 85 | 25.5 |  | 25.5
| h | Peons | pers_month | 0.2 | 85 | 17 |  | 17
|  | Sub total R.Staff Salary |  |  |  | 197 | 0 | 197 | 0
41420 | D.ii | Staff Allowances
| a | Travel allowance | pers_month | 0.25 | 85 | 21.25 |  | 21.25
| b | Deputation Hardship Allowance | pers_month | 0.1 | 85 | 8.5 |  | 8.5
| c | Obligatory provisions /e | pers_month | 0.21 | 20.47 | 9.03 | 4.73 | 4.3
|  | Sub total R. staff Allowances |  |  |  | 38.78 | 4.73 | 34.05 | 0
41410 | D.i | Staff salary (Contratual)
| a | Project Managers | pers_month | 0.2 | 68 | 17 | 3.4 | 13.6
| b | Junior Engineer (12 Contratual) | pers_month | 0.093 | 48 | 5.58 | 1.116 | 4.464
| c | Junier Clerk (Accountants) (1 Contractual) | pers_month | 0.052 | 4 | 0.26 | 0.052 | 0.208
| d | Social Mobiliser(8 Contratual) | pers_month | 0.052 | 32 | 2.08 | 0.416 | 1.664
| e | Project Assistants | pers_month | 0.1 | 68 | 8.5 | 1.7 | 6.8
| f | Data entry operators -MIS | pers_month | 0.052 | 68 | 4.42 | 0.884 | 3.536
|  | Sub total C. staff Salary |  |  |  | 37.84 | 7.568 | 30.272 | 0
41420 | D.ii | Staff Allowances
| a | Travel allowance | pers_month | 0.25 | 68 | 21.25 | 1.25 | 20
| b | Deputation Hardship Allowance | pers_month | 0.1 | 0 | 8.5 | 8.5 | 0
| c | Obligatory provisions /e | pers_month | 0.21 | 20 | 8.82 | 4.62 | 4.2
|  | Sub total C.staff Allowances |  |  |  | 38.57 | 14.37 | 24.2 | 0
|  | Sub total Staff Salary and Allowances |  |  |  | 312.19 | 26.668 | 285.522 | 0
41500 | E | Office operating costs |  |  |  | 47.26 |  | 26.01
41501 | i | Advertisement / Publicity | LS | 0.1 | 17 | 1.7 |  | 1.7
41502 | ii | Books and Periodicals | LS | 0.05 | 17 | 0.85 |  | 0.85
41503 | iii | Professional & Legal Charges | LS | 0.25 | 0 | 0 |  | 0
41504 | iv | Memberships and Subscription | pers_month |  |  | 0 |  | 0
41505 | v | Bank Charges | pers_month | 0.03 | 85 | 2.55 |  | 2.55
41506 | vi | Rates and Taxes | pers_month | 0.005 | 85 | 0.425 |  | 0.425
41507 | vii | Printing and Stationery | pers_month | 0.1 | 85 | 8.5 |  | 8.5
41508 | viii | Postage and Telegram | pers_month | 0.005 | 85 | 0.425 |  | 0.425
41509 | ix | Insurance of Assets | LS | 0.055 | 17 | 0.935 |  | 0.935
41510 | x | Arbitation Charges | LS |  |  | 0 |  | 0
41511 | xi | Hiring of Security Services | pers_month | 0.1 | 0 | 0 |  | 0
41512 | xii | Hiring of Auxiliary Services | LS |  |  | 0 |  | 0
41513 | xiii | Seminar/Conference | pers_month | 0.1 | 0 | 0 |  | 0
41514 | xiv | Office operating expenses | per month | 0.125 | 85 | 10.625 |  | 10.625
41515 | xv | Utilities | per month | 0.25 | 0 | 21.25 | 21.25 | 0
41516 | xvi | Office Rent | per month | 0.25 | 0 | 0 |  | 0
|  | Sub total Office Operating Costs |  |  |  | 47.26 | 21.25 | 26.01 | 0
41600 | F | Construction and Renovation of Buildings |  |  |  | 70
| 1A | New Office buildings /a | Each | 12.15 | 0 | 0 |  | 0
| 1B | Renovation of existing buildings | Each | 10 | 0 | 70 | 70 | 0
| 2C | Camp offices /b | Each | 16.2 | 0 | 0 |  | 0
|  | Sub total Buildings |  |  |  | 70 | 70 | 0 | 0
43000 | 4.3 | Sub- Component 4.3: Monitoring and Evaluation and KM |  |  |  | 47.1 | 27.9 | 19.2 | 0.07059
43100 | 1 | Start up workshop
| i | OPELIP startup at state level | event | 4 | 1 | 4 |  | 4
| ii | MPA level | event | 0.25 | 17 | 4.25 |  | 4.25
|  | Subtotal Start up workshop |  |  |  | 8.25 | 0 | 8.25 | 0
43200 | 2 | Monthly review meetings | [6 empty] | 0.07059
| i | at state level | meeting | 0.2 | 6 | 1.2 |  | 1.2 | 0.07059
| ii | at MPA level /a | meeting | 0.025 | 102 | 2.55 |  | 2.55
|  | Subtotal Monthly review meetings |  |  |  | 3.75 | 0 | 3.75 | 0.07059
43300 | 3 | Learning and sharing workshop
| i | Quality workshop at GP level /b | each | 0.05 | 84 | 4.2 |  | 4.2
| ii | Quality workshop at MPA level /c | each | 0.05 | 0 | 0 |  | 0
| iii | Quality workshop at PMU level /d | each | 0.5 | 0 | 0 |  | 0
|  | Subtotal Learning and sharing workshop |  |  |  | 4.2 | 0 | 4.2 | 0
43400 | 4 | Review workshop
43410 | 4A | MTR review | LS | 2.25 | 0 | 0 |  | 0
43420 | 4B | PCR review workshop | LS | 3.25 | 0 | 0 |  | 0
|  | Subtotal Review workshop |  |  |  | 0 | 0 | 0 | 0
43500 | 5 | Training
43510 | 5A.i | RIMS and M&E state level training | LS | 1 | 1 | 1 |  | 1
| 5A.ii | RIMS and M&E training at MPA level | LS | 0.75 | 0 | 12.75 | 12.75 | 0
43520 | 5B | Annual Outcome survey training | LS | 1 | 1 | 1 |  | 1
43530 | 5C | KAPS survey training | LS | 2.25 | 0 | 2.25 | 2.25 | 0
|  | Subtotal Training |  |  |  | 17 | 15 | 2 | 0
41330 | C.iii | Technical assistance
|  | M&E support | LS | 1.2 | 0 | 0 |  | 0
|  | Designing & functioning of web site & MIS software /e | LS | 40 | 1 | 2 | 1 | 1
|  | PME consultants | pers_month | 1.25 | 0 | 0 |  | 0
|  | Participatory M&E consultant | LS | 2 | 0 | 0 |  | 0
|  | Subtotal Technical assistance |  |  |  | 2 | 1 | 1 | 0
43600 | 6 | Concurrent monitoring by external Agency | MPA | 0.35 | 0 | 11.9 | 11.9
|  | Subtotal Concurrent monitoring /f |  |  |  | 11.9 | 11.9 | 0 | 0
|  | Grand Total (1+2+3+4) |  |  |  | 2575.9538 | 1476.0455 | 1099.897 | 7.3322
NB:
1.1. Community Institutions
\a Cost inclusive of the service tax of 12.5%
\b Wages at INR 4500/month for 80 MPW from April 2014 to March 2015
\c 10 from PMU and 3 each from MPA
\d 2 each from PMU and MPA
\e one each from MPA and NGO
\f 5 from each MPA and 12 from PMU
\g 4 persons per MPA for 5 days
\h 4 person per MPA for 2 days
\i 4 person per MPA for one day
\j One orientation training
\k Two day training
\l A two day training
\m 4 person per village
\n 4 person per village
\o 4 person per village
1.2. Stregthening SHGs and Rural Finance
\a 5 persons from each MPA
\b 3 per MPA
\c 3 per MPA
\d 6 staff per MPA
\e Two women per village
\f GP level cluster forums; 10 per GPLF and 2 from each village
\g One GPLF for each Gram Panchayat and 30 person from each GPLF
\h 3 persons from each GPLF
\i vrf-vulnerability reduction fund
\j SHG member
\k for piloting two cooperatives
\l 200 kg capacity bins per SHG targeted to PTG communities.
\m 75 kg dal per SHG per year for 2 year period;
\n Incentive to girls for marriage after 18 year
2.1. Natural Resource Management
\a A group of 15 to 20 persons from each village, for a 3 year period
\b one event day
\c one event day
\d 3 events one day each
\e Survey and demarcation of land for allotting land use rights
\f Actual reimbursement
\g Approx 20 ha of arable land, about 40 households per village;
\h each irrigates about 4 ha and benefits 20 households
\i 4 ha per village; crops include mango, cashew, orange, litchi etc
\j 20 households per village at INR 2000 per household
\k 20 households per village at INR 2500 per household
2.2. Food and Nutrition Security
\a Covered under Table 2.2
\b 2 SHG per village for 3 year period
\c Two demo per village for 3 year period
\d at least 2 FFS from each village
\e for one of three KVKs under OUAT
\f in particular for rain-fed crops
\g cultivation of nutrrition-dense crops; cost for supply of seeds, tools etc
\h 4 camps a year in each GP
2.3. Livelihoods Improvement
\a 2 per GP; cost for wages foregone; 30 days training at any KVK
\b 2 CSP per GP and training for 45 days
\c focus on pulses, oilseeds and millets
\d 2 per GP; cost inclusive of tools, seeds and low cost drip irrigation for a 400 sq ft area etc
\e 2 per GP
\f two CSP per GP; cost inclusive of shed, feed, chicks, wages
\g Two camp per year
\h all PTG households covered; support includes seeds, tools,training etc
\i Unspecified units; a lumpsum provision
\j one SHG per GP
\k set up near haat bazar and managed by TDCC
\l Two month training;
3.1. Community Infrastructure
\a 50% of villages
\b to be operated by any group.
\c to be operated by a group, CSP or SHG
3.2. Drudgery Reduction
\a 20 ha plot in each village & managed by women' group; cost inclusive of wages for 2 persons for 200 days plus planting materials
\b at each GP and to be managed by SHG or VDC; beneficiaries contribution in the form of labour
\c Organised by youth groups in respective GP
\d This is provided under Table 3.1, Community infrastructure
\e Fencing the sacred area within villages
4.1. Project Management Unit
\a fax machine, broadband connection, intercom, handycam, digital cameras,mobile, TV, LCD projector etc
\b Baseline survey using census approach;
\c Manual preparation, training to accountants etc
\d Services of a Deputy Secretary from the Revenue Department
\e Conveyance allowance, HRA, Medical Allowance, EPF- as per Govt., Communication allowance,etc
\f such as EPF, leave salary, gratuity
4.2. Micro-Project Agency Unit
\a with an area of 90 m3
\b with an area of 135 m3
\c fax machine, broadband connection, intercom, handycam, digital cameras, TV, LCD projector etc
\d Degree holding retired engineers; cost inclusive of DA and travel
\e such as EPF, leave salary, gratuity, medical, insurance etc
4.3. Monitoring and evaluation and KM
\a 204 meetings per year for 17 MPAs
\b one annual workshop at each GP
\c Quarterly workshop at each MPA
\d Quarlerly workshops
\e website, software, email ids etc.
\f to be carried out by external agencies on quarterly basis
NB:
PMU level staffs for 8 months
MPA level staffs for 5 months
NGO level staffs for 5 months
MPWs for GP for 4 months
Monthly review meeting for 4months

## Annexure-I with Achievement
Annexure-I
Code & Sub Code | Annual Work Plan Budget of OPELIP for the year 2016-17
| Sl No. | Component, Sub-component & Activities | Unit |  | AWPB for 2016-17 |  | Achievement
|  |  | Unit | Unit Cost (INR in Lakhs) | No of units | Total (INR in Lakhs) | Total (INR in Lakhs)
10000 | 1 | Component 1: Community Empowerment |  |  |  | 378.555
11000 | 1.1 | Sub- Component 1.1:Community Institutions Development |  |  |  | 368.055
11100 | 1 | Service provider contracts (NGO) |  |  |  | 311.83
|  | Year 1 (3 Months) | MPA | 18.34 | 17 | 311.83
|  | Year 2 /a | MPA | 70.47 | 0 | 0
|  | Year 3 | MPA | 70.47 | 0 | 0
|  | Year 4 | MPA | 70.47 | 0 | 0
|  | Year 5 | MPA | 68.1075 | 0 | 0
|  | Year 6 | MPA | 61.02 | 0 | 0
|  | Year 7 | MPA | 9.2475 | 0 | 0
|  | Year 8 | MPA | 0 | 0 | 0
11110 | 1A | Wages to MPWs /b | pers_month | 0.045 | 0 | 0
|  | Subtotal Service provider contracts (NGO) |  |  |  | 311.83
11200 | 2 | PMU & MPA Staff Exposure and Training |  |  |  | 16.8
11210 | i | Exposure visits- 7 days /c | pers_days | 0.075 | 183 | 13.72
11220 | ii | Nutrition & gender training /d | pers_days | 0.015 | 36 | 0.54
11230 | ii | Training for Junior engineers /e | pers_days | 0.015 | 72 | 1.08
11240 | iv | Programme concept & orientation /f | pers_days | 0.015 | 97 | 1.46
|  | PMU & MPA Staff Exposure and Training |  |  |  | 16.8
11300 | 3 | NGO staff Exposure and Training |  |  |  | 5.27
11210 | i | Exposure visits /g | pers_days | 0.05 | 85 | 4.25
11220 | ii | Nutrition & Gender training /h | pers_days | 0.0075 | 34 | 0.255
11240 | iii | Programme concept & orientation /i | pers_days | 0.0075 | 68 | 0.51
11250 | iv | NRM training 4 pers for 2 days | pers_days | 0.0075 | 34 | 0.255
|  | NGO staff Exposure and Training |  |  |  | 5.27
11400 | 4 | CRP training |  |  |  | 3.315
11240 | i | Programme concept & orientation /j | persons | 0.0015 | 510 | 0.765
11410 | ii | Community mobilisation, health & nutrition /k | person | 0.003 | 340 | 1.02
11420 | iii | VDP prepartion and book-keeping /l | person | 0.003 | 510 | 1.53
|  | Subtotal CRP training |  |  |  | 3.315
11500 | 5 | TOT Training module |  |  |  | 22.725
11510 | 5A | Hygeine & management of common diseases |  |  |  | 11.3625
| i | Resource Agency cost for TOT | pers_MPA | 0.5 | 17 | 8.5
| ii | Training arrangement | persons | 0.005 | 510 | 2.55
| iii | Training materials | LS | 0.1 | 1 | 0.1
| iv | Honorarium to the tranlator | session | 0.0025 | 85 | 0.2125
|  | Subtotal Hygeine & management of common diseases |  |  |  | 11.3625
11520 | 5B | Life skills education for girrls |  |  |  | 0
| i | Resource Agency cost for TOT | pers_MPA | 0.5 | 0 | 0
| ii | Training arrangement | persons | 0.005 | 0 | 0
| iii | Training materials | LS | 0.1 | 0 | 0
| iv | Honorarium to the tranlator | session | 0.0025 | 0 | 0
|  | Subtotal Life skills education for girls |  |  |  | 0
11530 | 5C | Women sexual and reproduction health |  |  |  | 0
| i | Resource Agency cost for TOT | pers_MPA | 0.5 | 0 | 0
| ii | Training arrangement | persons | 0.005 | 0 | 0
| iii | Training materials | LS | 0.1 | 0 | 0
| iv | Honorarium to the tranlator | session | 0.0025 | 0 | 0
|  | Subtotal Women sexual and reproduction health |  |  |  | 0
11540 | 5D | Confronting malaria |  |  |  | 11.3625
| i | Resource Agency cost for TOT | pers_MPA | 0.5 | 17 | 8.5
| ii | Training arrangement | persons | 0.005 | 510 | 2.55
| iii | Training materials | LS | 0.1 | 1 | 0.1
| iv | Honorarium to the tranlator | session | 0.0025 | 85 | 0.2125
|  | Subtotal Confronting malaria |  |  |  | 11.3625
|  | Subtotal TOT Training module |  |  |  | 22.725
11600 | 6 | Training VDA & VDC members on preparation of VDP |  |  |  | 8.115
11610 | 6A | VDP preparation training /m | village | 0.0075 | 541 | 4.0575
11620 | 6B | AWPB preparation training /n | village | 0.0075 | 0 | 0
11630 | 6C | Book-keeping training /o | village | 0.0075 | 541 | 4.0575
11640 | 6D | Audit of accounts | village | 0.005 | 0 | 0
|  | Subtotal Training VDA members |  |  |  | 8.115
11700 | 7 | Entry point interventions(EPI) | village | 1.75 | 0 | 0
|  | Subtotal Village development(EPI) |  |  |  | 0
12000 | 1.2 | Sub- Component 1.2: Stregthening SHGs and Rural Finance |  |  |  | 10.5
12100 | 1 | SHG formation & strengthening |  |  |  | 0
12110 | 1A | SHG mapping,audit & accounts |  |  |  | 0
| i | SHG mapping, audit etc | SHG | 0.005 | 0 | 0
| ii | Thematic exposure visits /a | SHG | 0.1 | 0 | 0
|  | Subtotal SHG mapping,audit & accounts |  |  |  | 0
12120 | 1B | SHG equipment: A/c books, Safe & calculators | SHG | 0.0195 | 0 | 0
|  | Subtotal SHG formation & strengthening |  |  |  | 0
12200 | 2 | TOT to NGO staff including CRPs |  |  |  | 10.5
12210 | 2A | SHG functioning |  |  |  | 5.25
| i | Resource agency cost for TOT /b | batch | 0.75 | 7 | 5.25
| ii | Training of CRPs 6 days | CRP_day | 0.03 | 0 | 0
| iii | Training SHG members | persons | 0.0035 | 0 | 0
| iv | Training Leaders for 2 days | persons | 0.007 | 0 | 0
| v | Training book-keepers, 2 days | persons | 0.007 | 0 | 0
|  | Subtotal SHG functioning |  |  |  | 5.25
12220 | 2B | Financial literacy, with 6 modules |  |  |  | 5.25
| i | Resource agency cost for TOT /c | persons | 0.75 | 7 | 5.25
| ii | Training of CRPs 4 days | CRP | 0.02 | 0 | 0
| iii | Training SHG members | persons | 0.0035 | 0 | 0
| iv | Training materials | LS | 1 | 0 | 0
|  | Subtotal Financial literacy, with 6 modules |  |  |  | 5.25
12230 | 2C | Gender training |  |  |  | 0
| i | Resource agency cost for TOT /d | persons | 0.5 | 0 | 0
| ii | Village volunteers /e | persons | 0.03 | 0 | 0
| iii | Training CRPs | persons | 0.0035 | 0 | 0
|  | Subtotal Gender training |  |  |  | 0
|  | Subtotal TOT to NGO staff including CRPs |  |  |  | 10.5
12300 | 3 | Rural Finance |  |  |  | 0
12310 | 3A | Capacity building of GPLF /f |  |  |  | 0
| i | MIS support to MPA | Lumpsum | 0.6 | 0 | 0
| ii | GPLF building & strenthening |  |  |  | 0
| a | Training on leadership & governance /g | person | 0.01 | 0 | 0
| b | Accounting training-2 days /h | person | 0.01 | 0 | 0
| c | Start up funds for furniture, bicycles etc | GPLF | 0.5 | 0 | 0
| d | Annual general body meeting | GPLF | 0.05 | 0 | 0
| e | Mobility expenses | LS | 0.025 | 0 | 0
| f | CRP salary | pers_month | 0.045 | 0 | 0
| g | Operating costs to GPLF (honorarium to members) | GPLF | 0.3 | 0 | 0
|  | Subtotal GPLF building & strenthening |  |  |  | 0
|  | Subtotal Capacity building of GPLF |  |  |  | 0
12320 | 3B | Funding support to SHG |  |  |  | 0
| i | Pro-poor Fund first instalment | member | 0.005 | 0 | 0
| ii | Pro-poor fund 2nd instalment | member | 0.005 | 0 | 0
| iii | VRF 1st & 2nd instalments/i | GPLF | 0.5 | 0 | 0
| iv | VRF 3rd and 4th instalments | GPLF | 0.75 | 0 | 0
| v | CIF first instalment /j | member | 0.022 | 0 | 0
|  | Subtotal Funding support to SHG |  |  |  | 0
12330 | 3C | Pilot on women cooperative |  |  |  | 0
| i | Feasibility study /k | study | 5 | 0 | 0
| ii | Exposure visits (in country) | persons | 0.05 | 0 | 0
| iii | Viability gap expenses | year | 5 | 0 | 0
| iv | Equipment & computer | LS | 0.75 | 0 | 0
| v | Staff training on cooperatives | person | 0.025 | 0 | 0
| vi | Training on governance & responsibilities | LS | 0.025 | 0 | 0
| vii | Legal assistance | LS | 0.03 | 0 | 0
| viii | Training on accounting & book-keeping | LS | 0.03 | 0 | 0
| ix | TA for hand-holding | year | 0.5 | 0 | 0
|  | Subtotal Pilot on women cooperative |  |  |  | 0
|  | Subtotal Rural Finance |  |  |  | 0
12400 | 4 | Nutrition and social issues |  |  |  | 0
12410 | 4A | Dal Poshak banks |  |  |  | 0
| i | Training CRPs and SHG | LS | 0.0025 | 0 | 0
| ii | Dal Bank equipment /l | SHG | 0.02 | 0 | 0
| iii | Supply of Dal /m | SHG | 0.0525 | 0 | 0
|  | Subtotal Dal Poshak banks |  |  |  | 0
12420 | 4B | Marriage incentives /n |  |  |  | 0
| i | Late marriage incentives to girls | person | 0.02 | 0 | 0
|  | SubtotalMarriage incentives |  |  |  | 0
|  | Subtotal Nutrition and social issues |  |  |  | 0
20000 | 2 | Component 2: Natural Resources mangementa nd Livelihood Improvemnet |  |  |  | 20.1
21000 | 2.1 | Sub- Component 2.1: Natural Resource Management |  |  |  | 10.1
21100 | 1 | Agriculture Training /a |  |  |  | 0
| 1A | Cereal crops SRI for rice, millet /b | person | 0.0015 | 0 | 0
| 1B | Pulses, oilseeds, tuber crops /c | person | 0.0015 | 0 | 0
| 1C | Horticulture /d | person | 0.0045 | 0 | 0
|  | Subtotal Agriculture Training |  |  |  | 0
21200 | 2 | Land Rights Allocation: RNGO /e |  |  |  | 10.1
| 2A | Training,workshop, review meetings /f | lumpsum |  |  | 10.1
| 2B | Identification of the Landless, mapping land allocation | lumpsum |  |  | 0
| 2C | Human resources costs- field level | lumpsum |  |  | 0
| 2D | Human resources costs, For RNGO | lumpsum |  |  | 0
| 2E | RNGO Management cost | lumpsum |  |  | 0
|  | Subtotal Land Rights Allocation: RNGO |  |  |  | 10.1
21300 | 3 | Natural Resource Management |  |  |  | 0
21310 | 3A | Land treatment /g | ha | 0.2 | 0 | 0
21320 | 3B | Irrigation structures /h | structure | 4 | 0 | 0
21330 | 3C | Horticulture plantation /i | village | 5 | 0 | 0
21340 | 3D | Cereal / millets crops development /j | village | 0.4 | 0 | 0
21350 | 3E | Pulses, oilseeds, tubers development /k | village | 0.5 | 0 | 0
|  | Subtotal Natural Resource Management |  |  |  | 0
22000 | 2.2 | Sub- Component 2.2: Food and Nutrition Security |  |  |  | 10
22100 | 1 | Food security |  |  |  | 0
22110 | 1A | PTG Food production system |  |  |  | 0
22111 | i | Farmers training /a | person | 0 | 0 | 0
22112 | ii | Onfarm demonstrations | village | 0.1 | 0 | 0
22113 | iii | Seed Production support /b | SHG | 0.1 | 0 | 0
22114 | iv | Compost-making /c | SHG | 0.05 | 0 | 0
|  | Subtotal PTG Food production system |  |  |  | 0
22120 | 1B | Farmers Field Schools, FFS |  |  |  | 0
| i | Formation/organisation of FFS /d | FSS | 0.01 | 0 | 0
| ii | Capacity building | FFS | 0.02 | 0 | 0
|  | Subtotal Farmers Field Schools, FFS |  |  |  | 0
22130 | 1C | Research and development support |  |  |  | 0
| i | R&D support on crop varities (OUAT) /e | LS | 75 | 0 | 0
| ii | Farmer-led crop trials /f | farmers | 0.1 | 0 | 0
|  | Subtotal Research and development support |  |  |  | 0
|  | Subtotal Food security |  |  |  | 0
22200 | 2 | Nutrition security |  |  |  | 10
22210 | 2A | Nutrition-dense crop diversification |  |  |  | 10
| i | Nutrition needs assessment | study | 5 | 0 | 5
| ii | Assessment of use and nutrient value of uncultivated foods | study | 5 | 0 | 5
| iii | Household crop development /g | farmers | 0.025 | 0 | 0
|  | Subtotal Nutrition-dense crop diversification |  |  |  | 10
22220 | 2B | Health camps /h | GP | 0.125 | 0 | 0
|  | Subtotal Health camps |  |  |  | 0
|  | Subtotal Nutrition security |  |  |  | 10
23000 | 2.3 | Sub- Component 2.3: Livelihoods Improvement |  |  |  | 0
23100 | 1 | Training Community Service Provider(CSP) |  |  |  | 0
| 1A | Agriculture and horticulture training /a | CSP | 0.005 | 0 | 0
| 1B | Livestock training /b | pers_day | 0.005 | 0 | 0
| 1C | IGA training | CSP | 0.005 | 0 | 0
|  | Subtotal Training CSP |  |  |  | 0
23200 | 2 | Support to CSPs in upscaling |  |  |  | 0
| 2A | Support for Crops diversification /c | CSP | 0.03 | 0 | 0
| 2B | Support for Kitchen garden /d | CSP | 0.05 | 0 | 0
| 2C | Support for horticulture 1st year /e | CSP | 0.17 | 0 | 0
| 2D | Support for horticulture 2nd year | CSP | 0.7 | 0 | 0
| 2E | Support for horticulture 3rd year | CSP | 0.3 | 0 | 0
|  | Subtotal Support to CSPs in upscaling |  |  |  | 0
23300 | 3 | Livestock demonstrations |  |  |  | 0
| 3A | Poultry mother units /f | CSP | 2 | 0 | 0
| 3B | Goat rearing unit (5+1) including shed | CSP | 0.3 | 0 | 0
| 3C | Animal health camps /g | MPA | 0.5 | 0 | 0
|  | Subtotal Livestock demonstrations |  |  |  | 0
23400 | 4 | Household production support |  |  |  | 0
| 4A | Kitchen gardens /h | household | 0.02 | 0 | 0
| 4B | Backyard Poultry (10 bird unit) | household | 0.03 | 0 | 0
| 4C | Goat rearing unit (5 does+1 buck) | household | 0.3 | 0 | 0
| 4D | IGA units /i | household | 0.3 | 0 | 0
|  | Subtotal Household production support |  |  |  | 0
23500 | 5 | Setting up of Producers Collectives |  |  |  | 0
23510 | 5A | Preparation of Feasibility Reports | per MPA | 1 | 0 | 0
23520 | 5B.i | LRA for Producer collectives | Collective | 7.5 | 0 | 0
| ii | Promotion of Livelihoods collectives | collective | 4 | 0 | 0
| iii | Infrastructure and equipment | Collective | 8 | 0 | 0
| iv | Hand-holding facilities | Collective | 1 | 0 | 0
|  | Subtotal Setting up of Producers Collectives |  |  |  | 0
23600 | 6 | Support for NTFP marketing |  |  |  | 0
23610 | 6A | Support for SHG,equipment for NTFP collection /j | per GP | 3 | 0 | 0
23620 | 6B | Haat bazar development for NTFP aggregation /k | per MPA | 25 | 0 | 0
|  | Subtotal Support for NTFP marketing |  |  |  | 0
23700 | 7 | Vocational Training /l | person | 0.3 | 0 | 0
|  | Subtotal Vocational Training |  |  |  | 0
30000 | 3 | Component 3: Community Infrastructure and Drudgery reduction. |  |  |  | 0
31000 | 3.1 | Sub- Component 3.1: Community Infrastructure |  |  |  | 0
31100 | 1 | Survey, preparation of feasibility reports |  |  |  | 0
| 1A | Feasibiltiy studies | GP | 5 | 0 | 0
| 1B | feasibility studies for micro-hydel | GP |  | 44 | 0
|  | Subtotal Survey, preparation of feasibility reports |  |  |  | 0
31200 | 2 | Drinking water & sanitation |  |  |  | 0
31210 | 2A | Gravity water supply | each | 5.25 | 0 | 0
31220 | 2B | Hand pumps | each | 1 | 0 | 0
31230 | 2C | Toilets | each | 0.15 | 0 | 0
31240 | 2D | Water Purification pilot | MPA | 4 | 0 | 0
|  | Subtotal Drinking water & sanitation |  |  |  | 0
31300 | 3 | Housing & habitat development |  |  |  | 0
31310 | 3A.i | Housing units | each | 1 | 0 | 0
| 3A.ii | Construction materials for house improvement | each | 0.4 | 0 | 0
31320 | 3B | CC road in villages /a | km | 5 | 0 | 0
|  | Subtotal Housing & habitat development |  |  |  | 0
31400 | 4 | Roads, electricity & solar lighting |  |  |  | 0
| 4A | Connecting roads, black-topped | km | 40 | 0 | 0
| 4B | Foot paths | km | 10 | 0 | 0
| 4C | Grid connection | km | 10 | 0 | 0
| 4D | Community solar lighting | each | 1 | 0 | 0
|  | Subtotal Roads, electricity & solar lighting |  |  |  | 0
31500 | 5 | Social infrastructure |  |  |  | 0
| 5A | Multi-purpose community hall | each | 5 | 0 | 0
| 5B | Primary Schools | each | 10 | 0 | 0
| 5C | School toilets | each | 1 | 0 | 0
|  | Subtotal Social infrastructure |  |  |  | 0
31600 | 6 | Economic Infrastructure |  |  |  | 0
| 6A | Drying yards | each | 2 | 0 | 0
| 6B | Market yards | each | 5 | 0 | 0
| 6C | Aggregation centres | each | 4 | 0 | 0
| 6D | SHG worksheds | each | 3 | 0 | 0
|  | Subtotal Economic Infrastructure |  |  |  | 0
31700 | 7 | Agricultural machinery & tools /b |  |  |  | 0
| 7A | Power tillers /c | set | 1.735 | 0 | 0
| 7B | Seed storage bins | each | 0.0035 | 0 | 0
|  | Subtotal Agricultural machinery & tools |  |  |  | 0
32000 | 3.2 | Sub- Component 3.2: Drudgery Reduction |  |  |  | 0
32100 | 1 | Drugery reduction interventions |  |  |  | 0
| 1A | Smokeless wood stoves | each | 0.015 | 0 | 0
| 1B | Solar lanterns | each | 0.05 | 0 | 0
| 1C | Community Fuelwood reserves /a | village | 0.2 | 0 | 0
| 1D | Milling units for millets, rice /b | each | 3 | 0 | 0
|  | Subtotal Drugery reduction interventions |  |  |  | 0
32200 | 2 | Tribal culture and values |  |  |  | 0
| 2A | Support to cultural festivals /c | GP | 0.5 | 0 | 0
| 2B | Community halls /d | GP |  | 0 | 0
| 2C | Youth dormentary | LS | 2 | 0 | 0
| 2D | Sacred Fencing /e | village | 0.05 | 0 | 0
|  | Subtotal Tribal culture and values |  |  |  | 0
32300 | 3 | Policy initiatives |  |  |  | 0
| 3A | Studies and surveys | MPA | 1 | 0 | 0
| 3B | Legal Advocacy | LS | 2 | 0 | 0
|  | Subtotal Policy initiatives |  |  |  | 0
40000 | 4 | Components 4 Programme Management |  |  |  | 701.242 | 7.3322
41000 | 4.1 | Sub- Component 4.1: Project Management Unit |  |  |  | 220.06 | 7.2616
41100 | A. | Vehicles |  |  |  | 4.8 | 0.11204
41101 | i | Procurement of Vehicles | Each | 7 | 0 | 0
41102 | ii | Hiring of Vehicles | pers_month | 0.8 | 6 | 4.8 | 0.11204
41103 | iii | Motor Cycles | each | 0.5 | 0 | 0
41104 | iv | POL for Vehicles and Motor Cycles | pers_month | 0.3 | 0 | 0
41105 | v | Maintenance of Vehicles/Motor Cycles etc | per month | 0.02 | 0 | 0
| A | Sub total Vehicles |  |  |  | 4.8 | 0.11204
41200 | B. | Equipments |  |  |  | 26.85 | 0.104
41201 | i | Computers Laptop | Each | 0.45 | 10 | 4.5
41202 | ii | Computer Desktop | Each | 0.35 | 5 | 1.75
41203 | iii | Printer,Scaner cum Photocopier (sets) | Each | 0.45 | 3 | 1.35
41204 | iv | Printer (Only) | each | 0.075 | 3 | 0.225 | 0.104
41205 | v | Scanner | each | 0.075 | 1 | 0.075
41206 | vi | Air conditioners | each | 0.4 | 8 | 3.2
41207 | vii | Water filters | each | 0.3 | 1 | 0.3
41208 | viii | Water Coolers | each | 0.12 | 0 | 0
41209 | ix | Ceiling fans | each | 0.035 | 10 | 0.35
41210 | x | Genset, silent mode | each | 4 | 0 | 0
41211 | xi | Invertors | each | 0.5 | 2 | 1
41212 | xii | Cameras | each | 0.075 | 0 | 0
41213 | xiii | EPBX Box | each | 0.2 | 1 | 0.2
41214 | xiv | Fax Machine | each | 0.15 | 1 | 0.15
41215 | xv | V sat / Broadband connection | each | 1.5 | 1 | 1.5
41216 | xvi | Intercom | each | 0.02 | 10 | 0.2
41217 | xvii | Handycam | each | 0.35 | 0 | 0
41218 | xviii | Digital cameras | each | 0.075 | 6 | 0.45
41219 | xix | Mobile | each | 0.1 | 11 | 1.1
41220 | xx | TV | each | 1 | 1 | 1
41221 | xxi | LCD projector | each | 1.5 | 1 | 1.5
41222 | xxii | Other equipment /a | each | 0.25 | 4 | 1
41223 | xxiii | Furniture set | Each | 5 | 1 | 5
41224 | xxiv | Office Renovation | LS | 2 | 1 | 2
|  | Sub total Equipments |  |  |  | 26.85 | 0.104
41300 | C | Surveys, audits and TA |  |  |  | 93.5
41310 | C.i | 1. Surveys and studies |  |  |  | 80
|  | Baseline survey /b | LS | 80 | 1 | 80
|  | RIMS baseline, MTR and endline | survey | 25 | 0 | 0
|  | Annual outcome survey | survey | 5 | 0 | 0
|  | MTR survey | survey | 10 | 0 | 0
|  | PCR study | study | 25 | 0 | 0
|  | Other studies | study | 5 | 0 | 0
|  | Subtotal Surveys and studies |  |  |  | 80 | 0
41320 | C.ii | Audits |  |  |  | 5.5
|  | Internal audit | year | 0.5 | 1 | 0.5
|  | Statutory audits | year | 2.5 | 0 | 0
|  | Preparation of Finance Manual /c | lumpsum | 5 | 0 | 0
|  | Tally software | lumpsum | 5 | 1 | 5
|  | Subtotal Audits |  |  |  | 5.5 | 0
41330 | C.iii | Technical assistance |  |  |  | 8
|  | National consultants | pers_month | 2 | 1 | 2
|  | Staff recruitment expenses | LS | 3 | 1 | 3 | 0.04
|  | NGO recruitment expenses | LS | 3 | 1 | 3
|  | Subtotal Technical assistance |  |  |  | 8 | 0.04
|  | Sub total Surveys, audits and TA |  |  |  | 93.5 | 0.04
41400 | D | Staff Salary and Allowances |  |  |  | 76.05 | 0
41410 | D.i | Staff salary |  |  |  | 56
| a | State Programme Director | pers_month | 1.25 | 8 | 10
| b | Deputy Programme Director | pers_month | 0.75 | 8 | 6
| c | Revenue Officer (Land rights) /d | pers_month | 0.5 | 0 | 0
| d | Senior Engineer | pers_month | 0.5 | 8 | 4
| e | Manager Finance | pers_month | 0.5 | 8 | 4 | 0.89
| f | PO(NRM) | pers_month | 0.5 | 8 | 4 | 0.5
| g | PO( L & C) | pers_month | 0.5 | 8 | 4
| h | PO(CB, Gender &Nutrition) | pers_month | 0.5 | 8 | 4 | 1
| i | Manager ( MIS and M&E) | pers_month | 0.5 | 8 | 4 | 1
| j | PO(CI & RF) | pers_month | 0.5 | 8 | 4 | 0.87
| k | Manager( GIS) | pers_month | 0.5 | 8 | 4 | 0.71
| l | System Analyst | pers_month | 0.25 | 8 | 2 | 0.5
| m | Manager, Communications & KM | pers_month | 0.5 | 0 | 0
| n | Accounts Assistants | pers_month | 0.2 | 16 | 3.2 | 0.75489
| o | Project Assistant MIS | pers_month | 0.25 | 0 | 0
| p | Executive Assistants | pers_month | 0.15 | 8 | 1.2 | 0.3
| q | Support staff | pers_month | 0.1 | 16 | 1.6 | 0.30605
| r | Drivers (supporting stff/ DEO) | pers_month | 0.15 | 0 | 0
|  | Sub total Staff Salary |  |  |  | 56 | 6.8309
41420 | D.ii | Staff Allowances |  |  |  | 20.05
| i | Travel allowance | pers_month | 1.25 | 8 | 10
| ii | Deputation Allowance | pers_month | 0.28 | 8 | 2.25
| iii | Obligatory provisions /e | pers_month | 0.725 | 8 | 5.8
| iv | Statutory provision(EPF)/f | pers_month | 0.25 | 8 | 2
|  | Sub total Staff Allowances |  |  |  | 20.05 | 0
|  | Sub total Staff Salary & Allowances |  |  |  | 76.05 | 6.8309
41500 | E | Office operating costs |  |  |  | 18.86
41501 | i | Advertisement / Publicity | LS | 2 |  | 2 | 0.1322
41502 | ii | Books and Periodicals | LS | 0.5 |  | 0.5
41503 | iii | Professional & Legal Charges | LS | 0.25 |  | 0.25
41504 | iv | Memberships and Subscription | pers_month |  |  | 0
41505 | v | Bank Charges | pers_month | 0.1 | 6 | 0.6
41506 | vi | Rates and Taxes | pers_month | 0.075 | 6 | 0.45
41507 | vii | Printing and Stationery | pers_month | 0.3 | 4 | 1.2
41508 | viii | Postage and Telegram | pers_month | 0.01 | 6 | 0.06 | 0.04242
41509 | ix | Insurance of Assets | LS | 0.1 |  | 0.1
41510 | x | Arbitation Charges | LS |  |  | 0
41511 | xi | Hiring of Security Services | pers_month | 0.1 | 12 | 1.2
41512 | xii | Hiring of Auxiliary Services | LS |  |  | 0
41513 | xiii | Seminar/Conference | pers_month | 0.1 | 5 | 0.5
41514 | xiv | Office operating expenses | per month | 2 | 4.5 | 9
41515 | xv | Utilities | per month | 0.4 | 0 | 0
41516 | xvi | Office Rent | per month | 0.75 | 4 | 3
|  | Sub total Office Operating Costs |  |  |  | 18.86 | 0.17462
42000 | 4.2 | Sub- Component 4.2: Micro-Project Agency Unit |  |  |  | 461.982 | 0
41100 | A. | Vehicles |  |  |  | 21.25
41101 | i | Procurement of Vehicles | Each | 7 | 0 | 0
41102 | ii | Hiring of Vehicles | Each | 0.25 | 85 | 21.25
41103 | iii | Motor Cycles | Each | 0.5 | 0 | 0
41104 | iv | POL for Vehicles and Motor Cycles | Each | 0.02 | 0 | 0
41105 | v | Maintenance of Vehicles/Motor Cycles etc | Each | 0.005 | 0 | 0
41106 | vi | Bycycles | Each | 0.03 | 0 | 0
| A | Sub total Vehicles |  |  |  | 21.25
41200 | B. | Equipments |  |  |  | 124.1
41201 | i | Computers Laptop | Each | 0.45 | 68 | 30.6
41202 | ii | Computer Desktop | Each | 0.35 | 68 | 23.8
41203 | iii | Printer,Scaner cum Photocopier (sets) | Each | 0.45 | 17 | 7.65
41204 | iv | Printer (Only) | Each | 0.075 | 17 | 1.275
41205 | v | Scanner | Each | 0.075 | 0 | 0
41206 | vi | Air conditioners | Each | 0.4 | 0 | 0
41207 | vii | Water filters | Each | 0.3 | 17 | 5.1
41208 | viii | Water Coolers | Each | 0.12 | 0 | 0
41209 | ix | Ceiling fans | Each | 0.035 | 85 | 2.975
41210 | x | Genset, silent mode | Each | 2 | 0 | 0
41211 | xi | Invertors | Each | 0.4 | 34 | 13.6
41212 | xii | Cameras | Each | 0.075 | 17 | 1.275
41213 | xiii | EPBX Box | each | 0.2 | 0 | 0
41214 | xiv | Fax Machine | each | 0.15 | 17 | 2.55
41215 | xv | V sat / Broadband connection | Each | 0.75 | 17 | 12.75
41216 | xvi | Intercom | each | 0.02 | 0 | 0
41217 | xvii | Handycam | each | 0.35 | 0 | 0
41218 | xviii | Digital cameras | each | 0.075 | 17 | 1.275
41219 | xix | Mobile | each | 0.1 | 0 | 0
41220 | xx | TV | each | 0.25 | 0 | 0
41221 | xxi | LCD projector | each | 0.65 | 0 | 0
41222 | xxii | Other equipment /a | Each | 0.25 | 17 | 4.25
41223 | xxiii | Furniture set | Each | 1 | 17 | 17
41224 | xxiv | Office Renovation | Each | 1 | 0 | 0
|  | Sub total Equipments |  |  |  | 124.1
41300 | C | Surveys, audits and Techinical Assistant(TA) |  |  |  | 5.1
| 3.i | Survey and Studies |  |  |  | 0
41320 | 3.ii | Audits |  |  |  | 5.1
|  | Internal audit | year | 0.3 | 17 | 5.1
|  | Statutory audits | year | 1 | 0 | 0
|  | Sub total Surveys,Audits |  |  |  | 5.1
41330 | 3.iii | Technical Assistant (Asst Engineers (Degree-holders)) /d | pers_days | 0.025 | 0 | 0
|  | Sub total TA Asst Engineers |  |  |  | 0
|  | Sub total Surveys, audits and TA |  |  |  | 5.1
41400 | D | Staff Salary and Allowances |  |  |  | 285.522
41410 | D.i | Staff salary (Regular) |  |  |  | 197
| a | Special Officer | pers_month | 0.6 | 85 | 51
| b | Junior Engineer (5 Regular) | pers_month | 0.6 | 25 | 15
| c | Junior Agricultural Officer | pers_month | 0.6 | 85 | 51
| d | Senior Clerk or Accountant (6 Regular) | pers_month | 0.3 | 30 | 9
| e | Junier Clerk (Accountants) (10 Regular) | pers_month | 0.3 | 50 | 15
| f | Field Assistant (Nutrition focal point) (9 Regular) | pers_month | 0.3 | 45 | 13.5
| g | Drivers | pers_month | 0.3 | 85 | 25.5
| h | Peons | pers_month | 0.2 | 85 | 17
|  | Sub total Staff Salary (Regular) |  |  |  | 197
41420 | D.ii | Staff Allowances (Regular) |  |  |  | 34.05
| a | Travel allowance | pers_month | 0.25 | 85 | 21.25
| b | Deputation Hardship Allowance | pers_month | 0.1 | 85 | 8.5
| c | Obligatory provisions /e | pers_month | 0.215 | 20 | 4.3
|  | Sub total staff Allowances(Regular) |  |  |  | 34.05
41410 | D.i | Staff salary (Contratual) |  |  |  | 30.272
| a | Project Managers | pers_month | 0.2 | 68 | 13.6
| b | Junior Engineer (12 Contratual) | pers_month | 0.093 | 48 | 4.464
| c | Junier Clerk (Accountants) (1 Contractual) | pers_month | 0.052 | 4 | 0.208
| d | Social Mobiliser(8 Contratual) | pers_month | 0.052 | 32 | 1.664
| e | Project Assistants | pers_month | 0.1 | 68 | 6.8
| f | Data entry operators -MIS | pers_month | 0.052 | 68 | 3.536
|  | Sub total staff Salary(Contractual) |  |  |  | 30.272
41420 | D.ii | Staff Allowances |  |  |  | 24.2
| a | Travel allowance | pers_month | 0.294 | 68 | 20
| b | Deputation Hardship Allowance | pers_month | 0.1 | 0 | 0
| c | Obligatory provisions /e | pers_month | 0.21 | 42 | 4.2
|  | Sub total staff Allowances(Contractual) |  |  |  | 24.2
|  | Sub total Staff Salary and Allowances |  |  |  | 240.736
41500 | E | Office operating costs |  |  |  | 26.01
41501 | i | Advertisement / Publicity | LS | 0.1 | 17 | 1.7
41502 | ii | Books and Periodicals | LS | 0.05 | 17 | 0.85
41503 | iii | Professional & Legal Charges | LS | 0.25 | 0 | 0
41504 | iv | Memberships and Subscription | pers_month |  |  | 0
41505 | v | Bank Charges | pers_month | 0.03 | 85 | 2.55
41506 | vi | Rates and Taxes | pers_month | 0.005 | 85 | 0.425
41507 | vii | Printing and Stationery | pers_month | 0.1 | 85 | 8.5
41508 | viii | Postage and Telegram | pers_month | 0.005 | 85 | 0.425
41509 | ix | Insurance of Assets | LS | 0.055 | 17 | 0.935
41510 | x | Arbitation Charges | LS |  |  | 0
41511 | xi | Hiring of Security Services | pers_month | 0.1 | 0 | 0
41512 | xii | Hiring of Auxiliary Services | LS |  |  | 0
41513 | xiii | Seminar/Conference | pers_month | 0.1 | 0 | 0
41514 | xiv | Office operating expenses | per month | 0.125 | 85 | 10.625
41515 | xv | Utilities | per month | 0.25 | 0 | 0
41516 | xvi | Office Rent | per month | 0.25 | 0 | 0
|  | Sub total Office Operating Costs |  |  |  | 26.01
41600 | F | Construction and Renovation of Buildings |  |  |  | 0
| 1A | New Office buildings /a | Each | 12.15 | 0 | 0
| 1B | Renovation of existing buildings | Each | 10 | 0 | 0
| 2C | Camp offices /b | Each | 16.2 | 0 | 0
|  | Construction and Renovation of Buildings |  |  |  | 0
43000 | 4.3 | Sub- Component 4.3: Monitoring and Evaluation and KM |  |  |  | 19.2 | 0.07059
43100 | 1 | Start up workshop |  |  |  | 8.25
| i | OPELIP startup at state level | event | 4 | 1 | 4
| ii | MPA level | event | 0.25 | 17 | 4.25
|  | Subtotal Start up workshop |  |  |  | 8.25 | 0
43200 | 2 | Monthly review meetings |  |  |  | 3.75 | 0.07059
| i | at state level | meeting | 0.2 | 6 | 1.2 | 0.07059
| ii | at MPA level /a | meeting | 0.025 | 102 | 2.55
|  | Subtotal Monthly review meetings |  |  |  | 3.75 | 0.07059
43300 | 3 | Learning and sharing workshop |  |  |  | 4.2
| i | Quality workshop at GP level /b | each | 0.05 | 84 | 4.2
| ii | Quality workshop at MPA level /c | each | 0.05 | 0 | 0
| iii | Quality workshop at PMU level /d | each | 0.5 | 0 | 0
|  | Subtotal Learning and sharing workshop |  |  |  | 4.2 | 0
43400 | 4 | Review workshop |  |  |  | 0
43410 | 4A | MTR review | LS | 2.25 | 0 | 0
43420 | 4B | PCR review workshop | LS | 3.25 | 0 | 0
|  | Subtotal Review workshop |  |  |  | 0 | 0
43500 | 5 | Training |  |  |  | 2
43510 | 5A.i | RIMS and M&E state level training | LS | 1 | 1 | 1
| 5A.ii | RIMS and M&E training at MPA level | LS | 0.75 | 0 | 0
43520 | 5B | Annual Outcome survey training | LS | 1 | 1 | 1
43530 | 5C | KAPS survey training | LS | 2.25 | 0 | 0
|  | Subtotal Training |  |  |  | 2 | 0
41330 | C.iii | Technical assistance |  |  |  | 1
|  | M&E support | LS | 1.2 | 0 | 0
|  | Designing & functioning of web site & MIS software /e | LS | 40 | 1 | 1
|  | PME consultants | pers_month | 1.25 | 0 | 0
|  | Participatory M&E consultant | LS | 2 | 0 | 0
|  | Subtotal Technical assistance |  |  |  | 1 | 0
43600 | 6 | Concurrent monitoring by external Agency | MPA | 0.35 | 0 | 0
|  | Subtotal Concurrent monitoring /f |  |  |  | 0 | 0
|  | Grand Total (1+2+3+4) |  |  |  | 1099.897
NB:
1.1. Community Institutions
\a Cost inclusive of the service tax of 12.5%
\b Wages at INR 4500/month for 80 MPW from April 2014 to March 2015
\c 10 from PMU and 3 each from MPA
\d 2 each from PMU and MPA
\e one each from MPA and NGO
\f 5 from each MPA and 12 from PMU
\g 4 persons per MPA for 5 days
\h 4 person per MPA for 2 days
\i 4 person per MPA for one day
\j One orientation training
\k Two day training
\l A two day training
\m 4 person per village
\n 4 person per village
\o 4 person per village
1.2. Stregthening SHGs and Rural Finance
\a 5 persons from each MPA
\b 3 per MPA
\c 3 per MPA
\d 6 staff per MPA
\e Two women per village
\f GP level cluster forums; 10 per GPLF and 2 from each village
\g One GPLF for each Gram Panchayat and 30 person from each GPLF
\h 3 persons from each GPLF
\i vrf-vulnerability reduction fund
\j SHG member
\k for piloting two cooperatives
\l 200 kg capacity bins per SHG targeted to PTG communities.
\m 75 kg dal per SHG per year for 2 year period;
\n Incentive to girls for marriage after 18 year
2.1. Natural Resource Management
\a A group of 15 to 20 persons from each village, for a 3 year period
\b one event day
\c one event day
\d 3 events one day each
\e Survey and demarcation of land for allotting land use rights
\f Actual reimbursement
\g Approx 20 ha of arable land, about 40 households per village;
\h each irrigates about 4 ha and benefits 20 households
\i 4 ha per village; crops include mango, cashew, orange, litchi etc
\j 20 households per village at INR 2000 per household
\k 20 households per village at INR 2500 per household
2.2. Food and Nutrition Security
\a Covered under Table 2.2
\b 2 SHG per village for 3 year period
\c Two demo per village for 3 year period
\d at least 2 FFS from each village
\e for one of three KVKs under OUAT
\f in particular for rain-fed crops
\g cultivation of nutrrition-dense crops; cost for supply of seeds, tools etc
\h 4 camps a year in each GP
2.3. Livelihoods Improvement
\a 2 per GP; cost for wages foregone; 30 days training at any KVK
\b 2 CSP per GP and training for 45 days
\c focus on pulses, oilseeds and millets
\d 2 per GP; cost inclusive of tools, seeds and low cost drip irrigation for a 400 sq ft area etc
\e 2 per GP
\f two CSP per GP; cost inclusive of shed, feed, chicks, wages
\g Two camp per year
\h all PTG households covered; support includes seeds, tools,training etc
\i Unspecified units; a lumpsum provision
\j one SHG per GP
\k set up near haat bazar and managed by TDCC
\l Two month training;
3.1. Community Infrastructure
\a 50% of villages
\b to be operated by any group.
\c to be operated by a group, CSP or SHG
3.2. Drudgery Reduction
\a 20 ha plot in each village & managed by women' group; cost inclusive of wages for 2 persons for 200 days plus planting materials
\b at each GP and to be managed by SHG or VDC; beneficiaries contribution in the form of labour
\c Organised by youth groups in respective GP
\d This is provided under Table 3.1, Community infrastructure
\e Fencing the sacred area within villages
4.1. Project Management Unit
\a fax machine, broadband connection, intercom, handycam, digital cameras,mobile, TV, LCD projector etc
\b Baseline survey using census approach;
\c Manual preparation, training to accountants etc
\d Services of a Deputy Secretary from the Revenue Department
\e Conveyance allowance, HRA, Medical Allowance, EPF- as per Govt., Communication allowance,etc
\f such as EPF, leave salary, gratuity
4.2. Micro-Project Agency Unit
\a with an area of 90 m3
\b with an area of 135 m3
\c fax machine, broadband connection, intercom, handycam, digital cameras, TV, LCD projector etc
\d Degree holding retired engineers; cost inclusive of DA and travel
\e such as EPF, leave salary, gratuity, medical, insurance etc
4.3. Monitoring and evaluation and KM
\a 204 meetings per year for 17 MPAs
\b one annual workshop at each GP
\c Quarterly workshop at each MPA
\d Quarlerly workshops
\e website, software, email ids etc.
\f to be carried out by external agencies on quarterly basis
NB:
PMU level staffs for 8 months
MPA level staffs for 5 months
NGO level staffs for 5 months
MPWs for GP for 4 months
Monthly review meeting for 4months